## Overview
Alafkar ERP ¦ HR UAT
76 test records • 36 use cases • 4 journeys • Initial state: Not run
Workstream | Total | Not run | Pass | Fail | Blocked | N/A | P0 not passed | Recorded / reviewed
Personnel and Employee Administration | 10 | 10 | 0 | 0 | 0 | 0 | 4 | 0
Recruitment and Hiring | 8 | 8 | 0 | 0 | 0 | 0 | 2 | 0
Attendance and Workforce Scheduling | 12 | 12 | 0 | 0 | 0 | 0 | 6 | 0
Leave Management | 10 | 10 | 0 | 0 | 0 | 0 | 8 | 0
Payroll and Compensation | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 0
Performance Management | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
Training and Development | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
Shared Reporting and Controls | 8 | 8 | 0 | 0 | 0 | 0 | 4 | 0
End-to-End Journeys | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 0
Total | 76 | 76 | 0 | 0 | 0 | 0 | 40 | 0
Preparation items still incomplete | 19
Unresolved critical / major issues | 0
Minor issues lacking closure or accepted workaround | 0
Evidence / disposition still incomplete | 76
Sign-offs still incomplete | 10
Decision support | Manual release review required
Start with Preparation, then filter Results by phase/workstream using Test Cases. Yellow cells are editable.
P0 = critical; P1 = required. All subscenarios must pass before a test record can Pass.
Do not mark missing functionality Pass. Log a capability gap. N/A needs owner approval and reviewer.
Counts support review; they do not verify evidence contents or authorize release. See docs/uat/hr/README.md.
Append issues inside the table; extend Overview formula ranges beyond the 40 reserved issue rows.
Retests: keep original actual/evidence, add dated retest evidence/build and update status only after review.

## Results
HR Results
Test ID | Workstream | Priority | Assigned tester | Test role / scope | Status | Actual result | Evidence location / IDs | Issue / gap IDs | Retest result / evidence | Executed date | Build / cycle | N/A owner / reason | Reviewer | Evidence check
HR-01-P | Personnel and Employee Administration | P1 |  |  | Not run | [8 empty] | Not run
HR-01-C | Personnel and Employee Administration | P1 |  |  | Not run | [8 empty] | Not run
HR-02-P | Personnel and Employee Administration | P1 |  |  | Not run | [8 empty] | Not run
HR-02-C | Personnel and Employee Administration | P1 |  |  | Not run | [8 empty] | Not run
HR-03-P | Personnel and Employee Administration | P1 |  |  | Not run | [8 empty] | Not run
HR-03-C | Personnel and Employee Administration | P1 |  |  | Not run | [8 empty] | Not run
HR-04-P | Personnel and Employee Administration | P0 |  |  | Not run | [8 empty] | Not run
HR-04-C | Personnel and Employee Administration | P0 |  |  | Not run | [8 empty] | Not run
HR-05-P | Personnel and Employee Administration | P0 |  |  | Not run | [8 empty] | Not run
HR-05-C | Personnel and Employee Administration | P0 |  |  | Not run | [8 empty] | Not run
REC-01-P | Recruitment and Hiring | P1 |  |  | Not run | [8 empty] | Not run
REC-01-C | Recruitment and Hiring | P1 |  |  | Not run | [8 empty] | Not run
REC-02-P | Recruitment and Hiring | P1 |  |  | Not run | [8 empty] | Not run
REC-02-C | Recruitment and Hiring | P1 |  |  | Not run | [8 empty] | Not run
REC-03-P | Recruitment and Hiring | P1 |  |  | Not run | [8 empty] | Not run
REC-03-C | Recruitment and Hiring | P1 |  |  | Not run | [8 empty] | Not run
REC-04-P | Recruitment and Hiring | P0 |  |  | Not run | [8 empty] | Not run
REC-04-C | Recruitment and Hiring | P0 |  |  | Not run | [8 empty] | Not run
ATT-01-P | Attendance and Workforce Scheduling | P1 |  |  | Not run | [8 empty] | Not run
ATT-01-C | Attendance and Workforce Scheduling | P1 |  |  | Not run | [8 empty] | Not run
ATT-02-P | Attendance and Workforce Scheduling | P1 |  |  | Not run | [8 empty] | Not run
ATT-02-C | Attendance and Workforce Scheduling | P1 |  |  | Not run | [8 empty] | Not run
ATT-03-P | Attendance and Workforce Scheduling | P0 |  |  | Not run | [8 empty] | Not run
ATT-03-C | Attendance and Workforce Scheduling | P0 |  |  | Not run | [8 empty] | Not run
ATT-04-P | Attendance and Workforce Scheduling | P1 |  |  | Not run | [8 empty] | Not run
ATT-04-C | Attendance and Workforce Scheduling | P1 |  |  | Not run | [8 empty] | Not run
ATT-05-P | Attendance and Workforce Scheduling | P0 |  |  | Not run | [8 empty] | Not run
ATT-05-C | Attendance and Workforce Scheduling | P0 |  |  | Not run | [8 empty] | Not run
ATT-06-P | Attendance and Workforce Scheduling | P0 |  |  | Not run | [8 empty] | Not run
ATT-06-C | Attendance and Workforce Scheduling | P0 |  |  | Not run | [8 empty] | Not run
LEV-01-P | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-01-C | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-02-P | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-02-C | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-03-P | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-03-C | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-04-P | Leave Management | P1 |  |  | Not run | [8 empty] | Not run
LEV-04-C | Leave Management | P1 |  |  | Not run | [8 empty] | Not run
LEV-05-P | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
LEV-05-C | Leave Management | P0 |  |  | Not run | [8 empty] | Not run
PAY-01-P | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-01-C | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-02-P | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-02-C | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-03-P | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-03-C | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-04-P | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-04-C | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-05-P | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-05-C | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-06-P | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PAY-06-C | Payroll and Compensation | P0 |  |  | Not run | [8 empty] | Not run
PER-01-P | Performance Management | P1 |  |  | Not run | [8 empty] | Not run
PER-01-C | Performance Management | P1 |  |  | Not run | [8 empty] | Not run
PER-02-P | Performance Management | P1 |  |  | Not run | [8 empty] | Not run
PER-02-C | Performance Management | P1 |  |  | Not run | [8 empty] | Not run
PER-03-P | Performance Management | P1 |  |  | Not run | [8 empty] | Not run
PER-03-C | Performance Management | P1 |  |  | Not run | [8 empty] | Not run
TRN-01-P | Training and Development | P1 |  |  | Not run | [8 empty] | Not run
TRN-01-C | Training and Development | P1 |  |  | Not run | [8 empty] | Not run
TRN-02-P | Training and Development | P1 |  |  | Not run | [8 empty] | Not run
TRN-02-C | Training and Development | P1 |  |  | Not run | [8 empty] | Not run
TRN-03-P | Training and Development | P1 |  |  | Not run | [8 empty] | Not run
TRN-03-C | Training and Development | P1 |  |  | Not run | [8 empty] | Not run
CTL-01-P | Shared Reporting and Controls | P1 |  |  | Not run | [8 empty] | Not run
CTL-01-C | Shared Reporting and Controls | P1 |  |  | Not run | [8 empty] | Not run
CTL-02-P | Shared Reporting and Controls | P0 |  |  | Not run | [8 empty] | Not run
CTL-02-C | Shared Reporting and Controls | P0 |  |  | Not run | [8 empty] | Not run
CTL-03-P | Shared Reporting and Controls | P1 |  |  | Not run | [8 empty] | Not run
CTL-03-C | Shared Reporting and Controls | P1 |  |  | Not run | [8 empty] | Not run
CTL-04-P | Shared Reporting and Controls | P0 |  |  | Not run | [8 empty] | Not run
CTL-04-C | Shared Reporting and Controls | P0 |  |  | Not run | [8 empty] | Not run
E2E-01 | End-to-End Journeys | P0 |  |  | Not run | [8 empty] | Not run
E2E-02 | End-to-End Journeys | P0 |  |  | Not run | [8 empty] | Not run
E2E-03 | End-to-End Journeys | P0 |  |  | Not run | [8 empty] | Not run
E2E-04 | End-to-End Journeys | P0 |  |  | Not run | [8 empty] | Not run

## Test Cases
HR Test Cases
Test ID | Parent use case | Workstream / owner | Phase | Priority | Scenario | Entry routes | Required fixture IDs | Steps — all listed variants | Acceptance criteria | Evidence required
HR-01-P | HR-01 | Personnel and Employee Administration HR operations manager | 1 | P1 | Maintain HR reference records — positive | /Employee/Position/List; /Employee/Specialization/List; /Employee/AcademicInistitution/List; /Employee/Teams | ORG; USERS; PEOPLE | Create one position, specialization, institution and team with UAT-prefixed bilingual names. Edit each. Refresh. Select the records in the relevant employee/team workflow and reopen the saved record. | All four records retain saved values. Selectors and team membership show the intended records in the correct company. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-01-C | HR-01 | Personnel and Employee Administration HR operations manager | 1 | P1 | Maintain HR reference records — control | /Employee/Position/List; /Employee/Specialization/List; /Employee/AcademicInistitution/List; /Employee/Teams | ORG; USERS; PEOPLE | With a read-only user attempt create/edit/delete for each type. With a specialist submit a foreign-company or nonexistent reference through the corresponding request. Reopen the original record. | Restricted writes and invalid references are rejected. Existing records and memberships remain unchanged. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-02-P | HR-02 | Personnel and Employee Administration HR operations manager | 1 | P1 | Create, edit, search and view employee — positive | /Employee/Employee/List; /Employee/Employee/Form/{Id:guid?}; /Employee/Employee/view/{Id:guid}; /Employee/Employee/360/{Id:guid} | ORG; USERS; PEOPLE | Create EMP-NEW using the prepared required fields and selected branch/department/position. Edit contact information. Search by the unique test name; apply company, branch and department filters. Refresh and compare list, profile and 360. | Exactly the intended employee is returned. Saved details and assignments agree across views and survive refresh. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-02-C | HR-02 | Personnel and Employee Administration HR operations manager | 1 | P1 | Create, edit, search and view employee — control | /Employee/Employee/List; /Employee/Employee/Form/{Id:guid?}; /Employee/Employee/view/{Id:guid}; /Employee/Employee/360/{Id:guid} | ORG; USERS; PEOPLE | Submit with each required field missing. Try a nonexistent and foreign-company department/position. Search for an absent name and move between pages of results. | Invalid records are not saved; validation identifies the issue. Empty search has no stale rows. Pagination does not mix or omit matching records. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-03-P | HR-03 | Personnel and Employee Administration HR operations manager | 1 | P1 | Maintain contacts, documents, skills and certificates — positive | /HR/EmployeeEmergencyContacts; /HR/EmployeeDocuments; /HR/EmployeeSkills | PEOPLE; FILES; USERS | Select EMP-REG. Add and edit a contact, document link, skill and certificate. Refresh each page. Open the document/certificate reference. Switch to EMP-NIGHT and back. | Values persist for EMP-REG; references open for the authorized tester. EMP-NIGHT has no copied records from EMP-REG. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-03-C | HR-03 | Personnel and Employee Administration HR operations manager | 1 | P1 | Maintain contacts, documents, skills and certificates — control | /HR/EmployeeEmergencyContacts; /HR/EmployeeDocuments; /HR/EmployeeSkills | PEOPLE; FILES; USERS | Attempt the same writes as a read-only user. Change the employee or child-record ID in a captured request to another company. Try an invalid document reference. | Unauthorized changes and foreign references fail without modifying either employee. Invalid references cannot be presented as successfully usable documents. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-04-P | HR-04 | Personnel and Employee Administration HR operations manager | 1 | P0 | Transfer, change position and process lifecycle — positive | /Employee/Employee/List; /HR/EmployeeLifecycle | PEOPLE; ORG; POLICY; USERS | Record EMP-MOVE current department, branch and position. Process separate transfer and position-change records. For each applicable lifecycle type create, approve and complete at the approved effective date. Refresh employee and event history. | Completed events apply the approved changes once and retain event history, actor and dates where required by POLICY. Employee assignments agree with the completed event. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-04-C | HR-04 | Personnel and Employee Administration HR operations manager | 1 | P0 | Transfer, change position and process lifecycle — control | /Employee/Employee/List; /HR/EmployeeLifecycle | PEOPLE; ORG; POLICY; USERS | Create separate events and cancel them before completion. Attempt completion without approval, repeat completion and attempt a transfer to a prohibited branch. | Cancelled events do not change assignments. Invalid/repeated transitions and prohibited transfers are rejected; neither branch gains unauthorized access. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-05-P | HR-05 | Personnel and Employee Administration HR operations manager | 1 | P0 | Terminate employee and reconcile downstream behavior — positive | /Employee/Employee/List; /HR/EmployeeLifecycle; /HR/Reports | PEOPLE; POLICY; PAYREF; USERS | Use EMP-EXIT with history and approved termination date/reason. Terminate through the available employee workflow. Refresh the profile and historical reports. Check future roster, attendance, leave and payroll eligibility against POLICY. | Termination details persist and historical records remain readable to authorized HR. Each downstream inclusion/exclusion matches the approved termination matrix; discrepancies are gaps. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
HR-05-C | HR-05 | Personnel and Employee Administration HR operations manager | 1 | P0 | Terminate employee and reconcile downstream behavior — control | /Employee/Employee/List; /HR/EmployeeLifecycle; /HR/Reports | PEOPLE; POLICY; PAYREF; USERS | Try termination as an unauthorized user; repeat a completed termination. Test dates before/on/after the effective date in downstream eligibility. Check that employee access follows POLICY. | Unauthorized/repeated actions cannot corrupt history. Boundary-date eligibility and account access match POLICY; absence of a required downstream control is a failure/gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-01-P | REC-01 | Recruitment and Hiring Recruitment lead | 2 | P1 | Maintain staffing plans and requisitions — positive | /HR/Recruitment | ORG; USERS; RECRUIT | Create a staffing plan for the test year and position. Create linked requisitions with planned headcount. Edit a draft, open it, then close it; use a separate requisition for cancellation. Refresh and filter. | Year, position, headcount, links and status persist. Open, closed and cancelled records appear under the matching filters. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-01-C | REC-01 | Recruitment and Hiring Recruitment lead | 2 | P1 | Maintain staffing plans and requisitions — control | /HR/Recruitment | ORG; USERS; RECRUIT | Attempt transitions from invalid states and repeat close/cancel. Submit missing required information and foreign-company position references. Repeat approval as a user without approval permission. | Invalid references, states and unauthorized approvals are rejected without changing the requisition. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-02-P | REC-02 | Recruitment and Hiring Recruitment lead | 2 | P1 | Register and progress applicants — positive | /HR/Recruitment | RECRUIT; USERS | Register two distinguishable applicants against separate requisitions. Move one through the available approved stages. Refresh; filter by requisition and status. | Details persist and each applicant stays linked to the correct requisition. Status filters return only matching applicants. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-02-C | REC-02 | Recruitment and Hiring Recruitment lead | 2 | P1 | Register and progress applicants — control | /HR/Recruitment | RECRUIT; USERS | Attempt an invalid stage transition and a foreign-company requisition reference. Repeat status change as a read-only user and search for an absent candidate. | Invalid/unauthorized changes fail; applicant association remains correct and empty filters show no stale candidate. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-03-P | REC-03 | Recruitment and Hiring Recruitment lead | 2 | P1 | Record interview feedback — positive | /HR/Recruitment | RECRUIT; USERS; POLICY | Open the intended applicant. Record interview feedback with the approved score scale and comments. Edit it; refresh and compare both applicants. | Scores/comments persist only on the intended applicant and match the approved score scale. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-03-C | REC-03 | Recruitment and Hiring Recruitment lead | 2 | P1 | Record interview feedback — control | /HR/Recruitment | RECRUIT; USERS; POLICY | Submit out-of-range scores or missing required feedback. Attempt edit/delete with a read-only user and change the applicant ID to another company. | Invalid scores and unauthorized changes fail; neither applicant receives another applicant’s feedback. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-04-P | REC-04 | Recruitment and Hiring Recruitment lead | 2 | P0 | Offer decision and employee handoff — positive | /HR/Recruitment; /Employee/Employee/Form/{Id:guid?} | RECRUIT; PEOPLE; USERS | Create an offer for the successful applicant. Accept it. Create/identify EMP-NEW through the employee workflow and link that employee to the accepted offer. Refresh offer and employee. Reject a separate offer. | Accepted/rejected statuses are correct. The hiring handoff references exactly EMP-NEW. Record whether employee creation is manual; offer acceptance alone is not proof of creation. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
REC-04-C | REC-04 | Recruitment and Hiring Recruitment lead | 2 | P0 | Offer decision and employee handoff — control | /HR/Recruitment; /Employee/Employee/Form/{Id:guid?} | RECRUIT; PEOPLE; USERS | Repeat acceptance and employee linking. Link a nonexistent or foreign-company employee; try linking a rejected offer. Repeat hire action without hire permission. | Invalid links/transitions fail; no duplicate employee or hire association appears; restricted users cannot complete hiring. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-01-P | ATT-01 | Attendance and Workforce Scheduling Attendance administrator | 2 | P1 | Configure shifts, calendar and assignments — positive | /Attendance/Shifts; /Attendance/ShiftAssignments; /Attendance/Holidays | CALENDAR; PEOPLE; USERS | Create day and overnight shifts. Configure working days and a holiday through the available configuration surface. Assign shifts with effective dates. Check employee preview/report before, on and after the assignment boundary. | The expected shift, holiday and work-day classification match CALENDAR at each tested date; saved configuration persists. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-01-C | ATT-01 | Attendance and Workforce Scheduling Attendance administrator | 2 | P1 | Configure shifts, calendar and assignments — control | /Attendance/Shifts; /Attendance/ShiftAssignments; /Attendance/Holidays | CALENDAR; PEOPLE; USERS | Try invalid shift times/assignments and unavailable employee references. Change configuration as a read-only user. Test holiday and weekend boundaries. | Invalid/unauthorized configuration does not save. Boundary classifications match the approved calendar; missing configuration UI is a gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-02-P | ATT-02 | Attendance and Workforce Scheduling Attendance administrator | 2 | P1 | Roster publication, swaps and substitutions — positive | /HR/AttendanceRoster | CALENDAR; PEOPLE; POLICY; USERS | Create a schedule and assign EMP-REG and EMP-NIGHT. Publish and verify each employee/date. Approve one swap and apply an approved substitution. Lock the schedule and refresh. | Published and changed assignments match the approved roster and are visible to the correct employees. Lock status persists. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-02-C | ATT-02 | Attendance and Workforce Scheduling Attendance administrator | 2 | P1 | Roster publication, swaps and substitutions — control | /HR/AttendanceRoster | CALENDAR; PEOPLE; POLICY; USERS | Cancel a separate swap and schedule. Try overlapping/invalid assignments, a prohibited-branch employee, and editing a locked schedule without authority. | Cancelled swaps do not apply. Invalid or prohibited assignments and unauthorized locked edits fail without changing the roster. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-03-P | ATT-03 | Attendance and Workforce Scheduling Attendance administrator | 2 | P0 | Sessions, breaks, overnight and missing checkout — positive | /Attendance/MyAttendance; /Attendance/Sessions | TIMELINE; PEOPLE; USERS | As EMP-REG check in, start/end a break and check out at recorded times. Repeat for EMP-NIGHT across midnight. Inspect sessions/report. Exercise missing-checkout resolution on a separate fixture. | Session date/time, break minutes and net work duration reconcile to TIMELINE. Overnight date attribution and missing-checkout handling match POLICY. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-03-C | ATT-03 | Attendance and Workforce Scheduling Attendance administrator | 2 | P0 | Sessions, breaks, overnight and missing checkout — control | /Attendance/MyAttendance; /Attendance/Sessions | TIMELINE; PEOPLE; USERS | Attempt two active sessions, ending before starting, duplicate checkout, and invalid break order. Attempt another employee’s session action. | Invalid sequences and foreign session actions fail; no duplicate sessions or negative durations are created. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-04-P | ATT-04 | Attendance and Workforce Scheduling Attendance administrator | 2 | P1 | Location rules and late/midday requests — positive | /Attendance/MyAttendance; /Attendance/LateRequests; /Attendance/PermissionRequests; /Attendance/ApprovePermissionRequests | GEO; TIMELINE; USERS; POLICY | Check in inside the approved geofence with accepted accuracy. Submit late and midday permission requests. Approve one of each as the intended reviewer; reject separate requests. Refresh status and attendance report. | Geofence result matches GEO. Each decision/comments persist; attendance treatment matches POLICY for approved versus rejected requests. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-04-C | ATT-04 | Attendance and Workforce Scheduling Attendance administrator | 2 | P1 | Location rules and late/midday requests — control | /Attendance/MyAttendance; /Attendance/LateRequests; /Attendance/PermissionRequests; /Attendance/ApprovePermissionRequests | GEO; TIMELINE; USERS; POLICY | Test outside boundary, denied/unavailable location, poor accuracy and mocked-location input. Try review without permission and repeat review of decided requests. | Each location condition has the approved explicit outcome. Unauthorized or repeated review cannot change attendance or silently approve the request. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-05-P | ATT-05 | Attendance and Workforce Scheduling Attendance administrator | 2 | P0 | Attendance correction and biometric import — positive | /HR/AttendanceRoster; /Attendance/Sessions | TIMELINE; BIO; USERS | Create and approve a correction for the known session, then apply it. Create a biometric batch with valid rows; review and post. Compare sessions and report to source timestamps. Locate the action UI or record a UI gap. | Only the intended session is corrected. Valid import rows yield the expected sessions; timestamps reconcile to BIO and retain source traceability. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-05-C | ATT-05 | Attendance and Workforce Scheduling Attendance administrator | 2 | P0 | Attendance correction and biometric import — control | /HR/AttendanceRoster; /Attendance/Sessions | TIMELINE; BIO; USERS | Reject a separate correction and try applying it. Import invalid employee/time rows, duplicate rows and repost the same batch. Attempt correction as an unauthorized user. | Rejected/unauthorized corrections do not apply. Invalid rows are identifiable; duplicate/reposted input cannot duplicate attendance. Backend-only capability does not pass manual UAT. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-06-P | ATT-06 | Attendance and Workforce Scheduling Attendance administrator | 2 | P0 | Generate, approve and lock work entries — positive | /HR/WorkEntries | TIMELINE; CALENDAR; LEAVEREF; USERS | Generate entries for the prepared employee/date range. Compare work, breaks and approved leave to reference totals. Approve and lock the entries. Refresh. | Entry population and quantities reconcile exactly to the approved attendance/leave reference; approval and lock states persist. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
ATT-06-C | ATT-06 | Attendance and Workforce Scheduling Attendance administrator | 2 | P0 | Generate, approve and lock work entries — control | /HR/WorkEntries | TIMELINE; CALENDAR; LEAVEREF; USERS | Regenerate the same range and attempt editing locked entries. Try approval without permission and include another company’s employee. | No duplicate or double-counted quantities result; locked/unauthorized changes and foreign-company entries are prevented. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-01-P | LEV-01 | Leave Management Leave administrator | 2 | P0 | Policies, periods and allocations — positive | /HR/LeavePolicies; /LeavesManagement/Balances | LEAVEREF; PEOPLE; USERS; POLICY | Create leave types, period, policy and employee policy assignments. Generate allocations for the prepared population. Compare balance and ledger to LEAVEREF; refresh. | Only assigned eligible employees receive the expected entitlement for the correct period and leave type. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-01-C | LEV-01 | Leave Management Leave administrator | 2 | P0 | Policies, periods and allocations — control | /HR/LeavePolicies; /LeavesManagement/Balances | LEAVEREF; PEOPLE; USERS; POLICY | Generate the same allocation again; try invalid periods, foreign-company assignments and unauthorized allocation. Inspect ledger and balances. | No duplicate entitlement is granted. Invalid/unauthorized allocations are rejected without changing balances. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-02-P | LEV-02 | Leave Management Leave administrator | 2 | P0 | Employee leave application — positive | /LeavesManagement/MyLeaveApplications | LEAVEREF; CALENDAR; FILES; USERS | As EMP-REG create a leave draft across the prepared workdays/holiday. Attach the synthetic document, submit and refresh. Compare charged days with LEAVEREF and open the attachment. | Dates/type/attachment persist; charged days match the approved calendar. Request belongs to the logged-in employee and reaches the intended submitted state. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-02-C | LEV-02 | Leave Management Leave administrator | 2 | P0 | Employee leave application — control | /LeavesManagement/MyLeaveApplications | LEAVEREF; CALENDAR; FILES; USERS | Test reversed dates, overlapping requests, insufficient balance, required attachment missing and a forged employee ID. Check existing requests and balance afterward. | Each condition follows POLICY with clear validation. No unintended request or balance transaction is created, and another employee cannot be impersonated. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-03-P | LEV-03 | Leave Management Leave administrator | 2 | P0 | Approve, reject and cancel leave — positive | /HR/LeaveApplications; /HR/LeaveLedger; /LeavesManagement/Reports | LEAVEREF; USERS; POLICY | Record starting balance. Approve a submitted application, reject a separate one and cancel the approved application using the permitted process. Inspect ledger and reports after each action. | Approval consumes exactly the expected days once; rejection consumes none; cancellation restores the correct amount. Decisions/comments and terminal requests appear in reports. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-03-C | LEV-03 | Leave Management Leave administrator | 2 | P0 | Approve, reject and cancel leave — control | /HR/LeaveApplications; /HR/LeaveLedger; /LeavesManagement/Reports | LEAVEREF; USERS; POLICY | Repeat approve/cancel; try review without authority and cancellation from a prohibited state. Compare balance/ledger before and after. | Repeated or unauthorized actions do not create extra debits/credits. Invalid transitions are rejected and ledger remains reconciled. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-04-P | LEV-04 | Leave Management Leave administrator | 2 | P1 | Emergency leave — positive | /LeavesManagement/EmergencyLeaves; /LeavesManagement/ApproveEmergencyLeaves | LEAVEREF; FILES; USERS; POLICY | Submit an emergency request with required reason/attachment. Approve it as the assigned reviewer and reject a separate request. Refresh and compare attendance and balance impact. | Requests, files, comments and decisions persist. Approved and rejected treatment match POLICY and LEAVEREF. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-04-C | LEV-04 | Leave Management Leave administrator | 2 | P1 | Emergency leave — control | /LeavesManagement/EmergencyLeaves; /LeavesManagement/ApproveEmergencyLeaves | LEAVEREF; FILES; USERS; POLICY | Test missing information, overlap, repeated review and review without permission. Attempt another employee/company request through a modified request. | Validation and access rules are enforced; rejected/duplicate requests do not silently consume leave or alter attendance. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-05-P | LEV-05 | Leave Management Leave administrator | 2 | P0 | Ledger adjustments and encashment — positive | /HR/LeaveLedger | LEAVEREF; PAYREF; USERS; POLICY | Record opening balance. Apply an authorized credit/debit adjustment with reason, then encash the approved days. Compare the ledger and any required payroll handoff with LEAVEREF/PAYREF. | Opening plus credits minus debits equals closing balance. Encashment days and amount match approved references; transactions remain traceable. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
LEV-05-C | LEV-05 | Leave Management Leave administrator | 2 | P0 | Ledger adjustments and encashment — control | /HR/LeaveLedger | LEAVEREF; PAYREF; USERS; POLICY | Repeat the same submission, request excess encashment, use invalid employee/type references and attempt an adjustment without permission. | No duplicate or unauthorized ledger/payroll transactions result. Excess/invalid requests follow POLICY; a missing required payroll handoff is recorded as a gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-01-P | PAY-01 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Components, contracts and structures — positive | /Payroll/Components; /Payroll/Contracts; /Payroll/AssignContract; /HR/PayrollStructures | PAYREF; PEOPLE; USERS; POLICY | Create earnings/deduction components, a contract and a salary structure. Assign appropriate fixtures with effective dates. Reopen and inspect before/on/after each effective boundary. | Amounts/formulas and assignment dates persist. The applicable salary basis is unambiguous and matches PAYREF for each boundary. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-01-C | PAY-01 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Components, contracts and structures — control | /Payroll/Components; /Payroll/Contracts; /Payroll/AssignContract; /HR/PayrollStructures | PAYREF; PEOPLE; USERS; POLICY | Attempt invalid amounts/formulas, conflicting effective assignments, foreign-company employee references and edits without permission. | Invalid/unauthorized assignments cannot create an ambiguous or unintended salary basis; errors identify rejected data. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-02-P | PAY-02 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Employee loans and installment recovery — positive | /Payroll/Loans; /HR/Payslips; /Payroll/SalaryRuns | PAYREF; PEOPLE; USERS; POLICY | Create and approve EMP-LOAN loan with the reference installment schedule. Process one eligible payroll installment. Inspect deduction and outstanding balance. Cancel a separate unused loan. | Only the approved eligible loan is recovered; installment and outstanding balance equal PAYREF; cancelled/unapproved loans are excluded. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-02-C | PAY-02 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Employee loans and installment recovery — control | /Payroll/Loans; /HR/Payslips; /Payroll/SalaryRuns | PAYREF; PEOPLE; USERS; POLICY | Recalculate/repeat payroll, reverse the installment via the permitted payroll process, and reprocess. Try unauthorized approval and cancellation after recovery. | Recovery occurs once; reversal restores the intended balance once. Subsequent cancellation follows POLICY without losing recovered history. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-03-P | PAY-03 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Salary-run workflow — positive | /Payroll/SalaryRuns | PAYREF; PEOPLE; USERS; POLICY | Create and calculate salary runs for the designated legacy-workflow fixtures. Compare gross/deductions/net independently. Approve and commit the period. Undo a separate disposable run/period using permitted controls. | Amounts match PAYREF to the approved rounding tolerance. Approval/commit/undo statuses and monetary side effects reconcile with the reference. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-03-C | PAY-03 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Salary-run workflow — control | /Payroll/SalaryRuns | PAYREF; PEOPLE; USERS; POLICY | Create the same employee-period twice; repeat approve/commit/undo; attempt undo without override authority; use an employee-period already processed through payroll entries. | No duplicate payout/accounting/recovery results across either workflow. Invalid/unauthorized actions fail; missing cross-workflow duplication control is a critical gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-04-P | PAY-04 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Payroll periods, entries, inputs and payslips — positive | /HR/Payslips; /HR/WorkEntries; /HR/SaudiPayroll | PAYREF; TIMELINE; LEAVEREF; USERS; POLICY | Open the reference period; create employee payroll inputs and import the approved attendance work entries. Create/generate an entry, inspect and recalculate payslips, approve, mark paid and close. Use separate fixtures to reopen/cancel. | Population, gross, deductions, net and loan balances match PAYREF. Attendance is counted once. Every allowed transition and resulting period/entry/payslip status persists. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-04-C | PAY-04 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Payroll periods, entries, inputs and payslips — control | /HR/Payslips; /HR/WorkEntries; /HR/SaudiPayroll | PAYREF; TIMELINE; LEAVEREF; USERS; POLICY | Repeat generation, work-entry import and paid action; attempt edits in a closed period, approval without authority and payroll for an ineligible employee. Compare totals before/after. | No duplicate slips, inputs or deductions. Closed/invalid states and unauthorized actions are blocked. Eligibility matches POLICY. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-05-P | PAY-05 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Payroll accounting posting — positive | /HR/Payslips | PAYREF; ACCOUNTING; USERS | Post the approved test payroll entry. Inspect resulting journals in accounting using Finance access. Compare company, branch, accounts, debit/credit and totals to ACCOUNTING. | Debits equal credits; journals match the payroll reference and intended company/branch. Posting links remain traceable. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-05-C | PAY-05 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Payroll accounting posting — control | /HR/Payslips | PAYREF; ACCOUNTING; USERS | Post again. On a separate fixture deliberately use incomplete accounting setup, inspect failure state, correct the setup and retry. Try posting without permission. | Repeated posting cannot duplicate journals. Failed posting leaves no partial/double posting; corrected retry succeeds once; unauthorized posting fails. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-06-P | PAY-06 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Saudi payroll, WPS and provision snapshots — positive | /HR/SaudiPayroll | PAYREF; WPS; EOS; USERS; POLICY | Enter approved employee payroll information/rates. Generate a WPS batch from eligible approved payslips; obtain the actual file and validate schema, employee population and totals against WPS. Create an EOS snapshot for the reference date and compare to EOS. | Inputs, calculations, WPS contents and EOS totals match the independently approved references. An actual consumable validated file is required to pass export; status alone is insufficient. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PAY-06-C | PAY-06 | Payroll and Compensation Payroll manager / Finance | 3 | P0 | Saudi payroll, WPS and provision snapshots — control | /HR/SaudiPayroll | PAYREF; WPS; EOS; USERS; POLICY | Use missing/invalid bank information, excluded employees and duplicate batch requests. Attempt exported-batch changes and snapshot creation without authority. Compare output again. | Invalid WPS records are exposed and cannot appear as successful output. No duplicate payment batch or unauthorized change. If export only changes status, log a blocking export gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PER-01-P | PER-01 | Performance Management Performance manager | 4 | P1 | Cycles, goals and competencies — positive | /HR/Performance | PERF; PEOPLE; USERS | Create an appraisal cycle, goal definitions and competencies. Assign the prepared employee goals with reference weights. Start the cycle; refresh and inspect associations. | Definitions, dates, weights and associations persist for the correct cycle and employees; available actions reflect the cycle state. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PER-01-C | PER-01 | Performance Management Performance manager | 4 | P1 | Cycles, goals and competencies — control | /HR/Performance | PERF; PEOPLE; USERS | Try invalid dates/weights, foreign-company employees, actions outside the active cycle and configuration without permission. | Invalid or unauthorized configuration/actions are rejected without corrupting the cycle or employee goals. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PER-02-P | PER-02 | Performance Management Performance manager | 4 | P1 | Scores, achievement and calculation — positive | /HR/Performance | PERF; USERS | Enter the reference achievement and competency scores. Create/recalculate the appraisal and compare components, weights, total and rating to the independent PERF calculation. | All score components and final rating match the approved reference/rounding. Recalculation yields the same result for unchanged inputs. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PER-02-C | PER-02 | Performance Management Performance manager | 4 | P1 | Scores, achievement and calculation — control | /HR/Performance | PERF; USERS | Submit out-of-range scores, missing required scores and invalid weights. Change one valid score, recalculate, then restore it and recalculate again. | Invalid inputs fail or visibly block a final result. Valid edits change the result as expected and restoration reproduces the reference total. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PER-03-P | PER-03 | Performance Management Performance manager | 4 | P1 | Appraisal submission, review and approval — positive | /HR/Performance | PERF; USERS; POLICY | Submit employee feedback, record manager review, approve and close the cycle. Use a separate appraisal for cancellation. Refresh evaluation/history. | Employee/manager feedback, decisions and final results persist in the correct sequence; cancelled records remain distinct from approved results. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
PER-03-C | PER-03 | Performance Management Performance manager | 4 | P1 | Appraisal submission, review and approval — control | /HR/Performance | PERF; USERS; POLICY | Attempt approval before review, employee self-approval, unauthorized access to another employee, and edits after finalization. Repeat final approval. | Role/state restrictions prevent unauthorized or repeated finalization and silent changes to finalized results. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
TRN-01-P | TRN-01 | Training and Development Training coordinator | 4 | P1 | Training programs and events — positive | /HR/Training | TRAIN; USERS | Create a program and dated event. Edit the draft; open, start and complete it. Create a separate event and cancel it. Refresh and filter program/status. | Program/event details and states persist; filters return the correct events and transitions follow the approved sequence. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
TRN-01-C | TRN-01 | Training and Development Training coordinator | 4 | P1 | Training programs and events — control | /HR/Training | TRAIN; USERS | Try reversed dates, invalid transition order, editing a completed event without authority and create/cancel as a read-only user. | Invalid/unauthorized actions fail without changing completed event data. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
TRN-02-P | TRN-02 | Training and Development Training coordinator | 4 | P1 | Enrollment, attendance and results — positive | /HR/Training | TRAIN; PEOPLE; USERS | Enroll EMP-REG and EMP-NIGHT in the event. Mark attended/absent respectively and record their distinct results. Refresh and compare attendee lists. | Correct employees are enrolled once; attendance/results remain associated with the intended attendee and event. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
TRN-02-C | TRN-02 | Training and Development Training coordinator | 4 | P1 | Enrollment, attendance and results — control | /HR/Training | TRAIN; PEOPLE; USERS | Enroll the same employee twice; submit a foreign-company employee and invalid result; record attendance/results without permission. | Duplicate/invalid enrollment and unauthorized writes fail; no result leaks to another attendee. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
TRN-03-P | TRN-03 | Training and Development Training coordinator | 4 | P1 | Certificates and training history — positive | /HR/Training; /HR/EmployeeSkills; /HR/Reports | TRAIN; FILES; PEOPLE; POLICY; USERS | Link the synthetic certificate to the completed attendee. Open it and inspect event/employee training history. Compare any required employee-certification synchronization against POLICY. | Certificate opens for the authorized user and belongs to the correct attendee; history reconciles with completed events. Required synchronization is demonstrated or logged as a gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
TRN-03-C | TRN-03 | Training and Development Training coordinator | 4 | P1 | Certificates and training history — control | /HR/Training; /HR/EmployeeSkills; /HR/Reports | TRAIN; FILES; PEOPLE; POLICY; USERS | Try an invalid certificate link, another attendee/company ID and unauthorized access. Inspect history for an absent or cancelled attendee. | Invalid/unauthorized certificate access and association fail. History does not falsely show completion or certification for cancelled/absent attendees. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-01-P | CTL-01 | Shared Reporting and Controls HR manager / system administrator | 1 | P1 | Dashboards, reports and exports — positive | /Employee/Dashboard; /HR/Reports; /Attendance/Reports; /LeavesManagement/Reports | REPORTREF; USERS | For each HR area, record filter values and run the matching report/dashboard. Compare record IDs, counts and monetary/time totals with REPORTREF. Export where offered and compare file contents. | Displayed and exported populations/totals agree with the same reference and filters. Required but unavailable reporting/export is recorded as a gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-01-C | CTL-01 | Shared Reporting and Controls HR manager / system administrator | 1 | P1 | Dashboards, reports and exports — control | /Employee/Dashboard; /HR/Reports; /Attendance/Reports; /LeavesManagement/Reports | REPORTREF; USERS | Test no-match filters, date cutoffs, branch changes and pagination. Export after changing filters; inspect for stale or out-of-scope records. | Empty views show no stale totals. Boundary, paginated and exported data respect filters and access scope. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-02-P | CTL-02 | Shared Reporting and Controls HR manager / system administrator | 1 | P0 | Role, employee, company and branch access — positive | All HR routes and their corresponding API requests | USERS; ORG; PEOPLE; POLICY | For every workstream use its specialist, approver and employee test accounts. Exercise the permitted reads/writes. Repeat branch reads as the restricted manager and separately as the explicitly authorized view-all user. | Allowed operations work only within assigned role, employee and company/branch scope. View-all scope does not grant missing action permission. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-02-C | CTL-02 | Shared Reporting and Controls HR manager / system administrator | 1 | P0 | Role, employee, company and branch access — control | All HR routes and their corresponding API requests | USERS; ORG; PEOPLE; POLICY | For every workstream try read/create/edit/delete/approve as applicable with the permission removed. Replay corresponding requests using another employee/company/branch ID. Include no-HR-access and signed-out sessions; test transfer source and destination. | Server rejects prohibited operations and discloses no protected data. Hidden buttons alone are insufficient. Record each endpoint/action/identity combination and expected denial in evidence. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-03-P | CTL-03 | Shared Reporting and Controls HR manager / system administrator | 1 | P1 | Arabic and English usability — positive | All HR list/form/approval/report routes | USERS; PEOPLE | In each workstream open a list and form; enter unsaved synthetic values. Toggle English/Arabic in both directions, then save. Inspect labels, direction, selectors, validation and tables. | Language and direction update without losing values; controls, names, dates and numbers remain readable and usable; saved business values remain the same. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-03-C | CTL-03 | Shared Reporting and Controls HR manager / system administrator | 1 | P1 | Arabic and English usability — control | All HR list/form/approval/report routes | USERS; PEOPLE | Repeat toggle during validation, with long Arabic/English names, in modals and at a narrow viewport. Inspect approval and report controls for clipping or inaccessible actions. | Errors/actions remain understandable and reachable. Toggle does not reset selected employee, duplicate save or reverse business values. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-04-P | CTL-04 | Shared Reporting and Controls HR manager / system administrator | 1 | P0 | Failures, validation and repeat actions — positive | All HR create/edit/approval routes | USERS; POLICY | For each workstream save a valid record and refresh. In the isolated UAT session simulate a failed request, observe feedback, restore connectivity and retry using the same fixture. | Committed values survive refresh. Failed requests do not show success; retry produces the intended single committed change. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
CTL-04-C | CTL-04 | Shared Reporting and Controls HR manager / system administrator | 1 | P0 | Failures, validation and repeat actions — control | All HR create/edit/approval routes | USERS; POLICY | Double-click save/approve, repeat the same request, submit invalid fields and refresh during a failed save. Compare record and transaction counts before/after. | No duplicate business transaction or partial update is hidden. Clear errors preserve recoverable input; repeated actions cannot falsely succeed. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
E2E-01 | E2E-01 | End-to-End Journeys UAT coordinator / workstream owners | 5 | P0 | Recruit to salary assignment | /HR/Recruitment; /Employee/Employee/List; /HR/PayrollStructures | RECRUIT; PEOPLE; PAYREF; USERS | Create/open requisition; register applicant; record interview; accept offer; create/identify employee and link offer; assign salary basis. Refresh each stage and capture IDs. | One applicant, accepted offer and employee are linked correctly; the employee has the approved effective salary assignment. Manual handoffs are documented; no automatic creation is assumed. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
E2E-02 | E2E-02 | End-to-End Journeys UAT coordinator / workstream owners | 5 | P0 | Attendance to accounting | /Attendance/MyAttendance; /HR/AttendanceRoster; /HR/WorkEntries; /HR/SaudiPayroll; /HR/Payslips | TIMELINE; LEAVEREF; PAYREF; ACCOUNTING; USERS | Record session; approve/apply correction; generate, approve and lock work entry; import once to payroll; generate and approve payslip; post accounting. Compare quantities and amounts at every handoff. | Session, work entry, payroll input, payslip and journal IDs are traceable. Hours and money reconcile without duplicate consumption or posting. Missing action UI is a gap. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
E2E-03 | E2E-03 | End-to-End Journeys UAT coordinator / workstream owners | 5 | P0 | Leave allocation to cancellation | /HR/LeavePolicies; /LeavesManagement/MyLeaveApplications; /HR/LeaveApplications; /HR/LeaveLedger; /Attendance/Reports | LEAVEREF; CALENDAR; USERS | Allocate entitlement; employee submits leave; manager approves; inspect attendance and payroll-facing work entries; reconcile balance; cancel through permitted process and reconcile again. | Approval affects intended days once; cancellation restores correct leave/attendance treatment. Opening, debit, reversal and closing amounts reconcile across screens. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.
E2E-04 | E2E-04 | End-to-End Journeys UAT coordinator / workstream owners | 5 | P0 | Transfer and termination downstream | /Employee/Employee/List; /HR/EmployeeLifecycle; /HR/AttendanceRoster; /HR/Payslips; /HR/Reports | PEOPLE; POLICY; PAYREF; USERS | Transfer EMP-MOVE and check source/destination access, roster, leave, payroll and reporting at effective dates. Separately terminate EMP-EXIT and repeat downstream eligibility/access checks. | Every downstream behavior agrees with the approved transfer/termination matrix; history remains available to authorized HR. Each missing control is linked to an issue and owner. | Before/after IDs, screenshots or request/response outcome, calculations/files where applicable. Identify every subscenario and role.

## Preparation
HR Preparation
Ready requires actual IDs or an approved reference AND approver/date; placeholders are not approved baselines.
Fixture ID | Requirement | Owner | Required content | Status | Actual IDs / approved reference / evidence | Approved by / date | Ready with evidence (1/0)
ENV | Environment | UAT coordinator | Record UI/API URL, isolated database, release/commit, deployment time, browser/device and UAT cycle. Confirm backup/reset procedure. | Not ready |  |  | 0
ORG | Organizations | System administrator | Create UAT-CO-A and UAT-CO-B; A-MAIN and A-SECOND branches; two departments and positions. Record real generated IDs. No production records. | Not ready |  |  | 0
USERS | Accounts and access | System administrator | Create HR admin, specialists per area, approver, two branch-restricted managers, two employee accounts, read-only and no-HR-access users. Record action permissions and explicit scope; never passwords/tokens. | Not ready |  |  | 0
PEOPLE | Employee fixtures | HR operations manager | Create EMP-NEW, EMP-REG, EMP-NIGHT, EMP-LOAN, EMP-MOVE and EMP-EXIT in A; another employee in B. Map each alias to actual ID, branch, department, position, dates and user. Separate disposable variants for destructive tests. | Not ready |  |  | 0
POLICY | Approved business rules | HR / Payroll owners | Attach signed/versioned rules for approval authority, leave days/overlap/negative balance, location handling, effective dates, termination and transfer downstream treatment, training synchronization and payroll rounding. Identify production payroll workflow. | Not ready |  |  | 0
CALENDAR | Working calendar | Attendance / Leave owners | Choose full payroll month; list workdays, weekends, holidays, day and overnight shift dates. Approve expected leave-day and overnight-date attribution. Use Asia/Riyadh display and record UTC equivalents. | Not ready |  |  | 0
TIMELINE | Attendance references | Attendance administrator | Independent timestamp reference: normal day, break, overnight, late arrival, missing checkout and correction. Approve expected gross/break/net minutes per date plus approved leave inputs. | Not ready |  |  | 0
GEO | Location cases | Attendance administrator | Record test geofence, approved in/out/boundary coordinates and accuracy; expected outcomes for denied/unavailable, low accuracy and mocked location. Use test device. | Not ready |  |  | 0
BIO | Biometric import rows | Attendance administrator | Synthetic valid, duplicate, invalid-employee and invalid-time rows with expected sessions and counts. Record source timezone, device identifier and batch IDs. | Not ready |  |  | 0
FILES | Synthetic attachments | HR operations manager | Prepare accessible synthetic document and certificate files plus missing/invalid references. Record permitted test attachment types and access expectations. | Not ready |  |  | 0
RECRUIT | Hiring fixtures | Recruitment lead | One staffing plan, two requisitions, two applicants, scored interview, accepted and rejected offers. Approve score scale, transitions and manual employee-creation handoff. | Not ready |  |  | 0
LEAVEREF | Leave reference ledger | Leave administrator | Independently approve per-employee/type/period opening, allocation, adjustment, approval debit, rejection zero, cancellation reversal and encashment debit. Record expected closing after each step. | Not ready |  |  | 0
PAYREF | Payroll reference sheet | Payroll manager | Approve one full-period employee population; salary components, effective assignments, attendance quantities, prorating, loan installments, rates, gross/deductions/net and rounding tolerance. Separate legacy/entry fixtures plus a cross-workflow duplicate fixture. Do not copy application output as expected values. | Not ready |  |  | 0
ACCOUNTING | Accounting reference | Finance | Approve per-company/branch journals/accounts and expected debits/credits and payroll reconciliation. Prepare a disposable missing-configuration fixture for failed-posting recovery. | Not ready |  |  | 0
WPS | WPS output specification | Payroll / Finance | Supply approved recipient file format, sample/schema, eligible population, bank-data validation and expected payment totals. Export status alone is not evidence of a file. | Not ready |  |  | 0
EOS | End-of-service reference | Payroll / Finance | Supply approved calculation method/rates, employee inputs, service dates, reference date and expected provision amounts. No legal-rate assumptions from code defaults. | Not ready |  |  | 0
PERF | Appraisal reference | Performance manager | Approve cycle, two employees, goals/weights, competencies, score ranges, independently calculated components/total/rating, and allowed transition roles. | Not ready |  |  | 0
TRAIN | Training fixtures | Training coordinator | Create program/event; two attendees with distinct attendance/results; approved completion/certificate rules and employee-history expectations. | Not ready |  |  | 0
REPORTREF | Report controls | Workstream owners | Approve record-ID populations and counts/totals by employee, date, company and branch for every HR report; include no-match, boundary and pagination examples. | Not ready |  |  | 0

## Issues
HR Issues
Issue ID | Test IDs | Type | Severity | Summary / reproduction | Expected / actual | Evidence | Owner | Status | Workaround / acceptance | Target date | Retest evidence / build | Minor still open (1/0)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Sign-off
HR Signoff
Owner role | Area | Review requirement | Decision | Named approver | Date | Evidence / accepted minor issue IDs | Comments | Approved with evidence (1/0)
HR operations manager | Personnel / lifecycle | All HR cases, E2E-01 and E2E-04; historical and downstream behavior | Pending |  |  |  |  | 0
Recruitment lead | Recruitment | All REC cases and E2E-01; hiring handoff | Pending |  |  |  |  | 0
Attendance administrator | Attendance | All ATT cases and E2E-02; minutes and work-entry reconciliation | Pending |  |  |  |  | 0
Leave administrator | Leave | All LEV cases and E2E-03; ledger reconciliation | Pending |  |  |  |  | 0
Payroll manager | Payroll | All PAY cases, E2E-02 / E2E-04; approved reference amounts and production workflow | Pending |  |  |  |  | 0
Finance | Payroll accounting / output | PAY-05 / PAY-06; journals, WPS usable file and provision references | Pending |  |  |  |  | 0
Performance manager | Performance | All PER cases; independent score calculation | Pending |  |  |  |  | 0
Training coordinator | Training | All TRN cases; employee history and certificates | Pending |  |  |  |  | 0
System administrator | Access controls | CTL-02 for every HR workstream and transfer source/destination | Pending |  |  |  |  | 0
HR manager | Operational release acceptance | All critical cases passed; all other cases passed or owner-dispositioned; no unresolved critical/major issues; accepted minor issues have workaround, owner and date | Pending |  |  |  |  | 0