## Summary
ERP User Role UAT Tracker | ERP User Role UAT Tracker | ERP User Role UAT Tracker | ERP User Role UAT Tracker | ERP User Role UAT Tracker | ERP User Role UAT Tracker | ERP User Role UAT Tracker | ERP User Role UAT Tracker
Metric | Value |  | Status | Formula | Current Count | Notes
Total cases | 55 |  | Not Run |  | 0 | Default status before execution
P0 cases | 37 |  | In Progress |  | 0 | Use while actively testing
P1 cases | 14 |  | Passed |  | 0 | Expected and actual results match
P2 cases | 4 |  | Failed |  | 0 | Open defect required
Roles covered | 11 |  | Blocked |  | 0 | Cannot execute due to missing setup/environment
Execution sequence
1 | Run login, authorization, and localization checks for each role.
2 | Execute P0 cases before P1/P2 cases.
3 | Record entity IDs, before/after status, screenshots, and defect links.
4 | For negative tests, verify no data, stock, payroll, balance, or status changed.
5 | Retest affected cases after role or permission changes.

## Test Cases
Case ID | Module | Role | Feature | Scenario | Prerequisites | Steps | Test Data | Expected Result | Negative/Positive | Required Permissions | Route | Priority | Status | Actual Result | Evidence | Defect ID | Tester | Date
UAT-001 | Auth | All roles | Login | Log in with valid assigned user and open the default dashboard/menu. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as All roles. 2. Navigate to `/login`. 3. Execute scenario: Log in with valid assigned user and open the default dashboard/menu.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Login succeeds; menu shows only items allowed by the user's permission claims. | Positive | Valid user credentials | `/login` | P0 | Not Run
UAT-002 | Auth | All roles | Login | Try invalid password and expired/disabled user if available. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as All roles. 2. Navigate to `/login`. 3. Execute scenario: Try invalid password and expired/disabled user if available.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Login is rejected; protected routes remain inaccessible. | Negative | None | `/login` | P0 | Not Run
UAT-003 | Security | All roles | Authorization | Paste a route that the role does not have permission to view. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as All roles. 2. Navigate to Any protected route. 3. Execute scenario: Paste a route that the role does not have permission to view.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Page blocks access or actions are hidden/disabled; backend rejects direct action attempt. | Negative | Missing target permission | Any protected route | P0 | Not Run
UAT-004 | UX | All roles | Localization | Toggle English/Arabic and navigate a list and form page. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as All roles. 2. Navigate to Any allowed page. 3. Execute scenario: Toggle English/Arabic and navigate a list and form page.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Text, direction, layout spacing, and action alignment remain usable in both languages. | Positive | Any allowed page permission | Any allowed page | P2 | Not Run
UAT-005 | Attendance | Regular employee | My attendance | Open My Attendance and perform the normal daily attendance action available in the page. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/Attendance/MyAttendance`. 3. Execute scenario: Open My Attendance and perform the normal daily attendance action available in the page.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Attendance action succeeds; latest session/status updates for the logged-in employee only. | Positive | `Attendance.Attendance.Create` | `/Attendance/MyAttendance` | P0 | Not Run
UAT-006 | Attendance | Regular employee | My attendance validation | Repeat an attendance action that is no longer valid for the current state. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/Attendance/MyAttendance`. 3. Execute scenario: Repeat an attendance action that is no longer valid for the current state.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Duplicate or invalid state transition is rejected with a visible validation/error message. | Negative | `Attendance.Attendance.Create` | `/Attendance/MyAttendance` | P0 | Not Run
UAT-007 | Leave | Regular employee | Emergency leave request | Create an emergency leave request for an available date and reason. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/LeavesManagement/EmergencyLeaves`. 3. Execute scenario: Create an emergency leave request for an available date and reason.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request is saved as pending and appears in the employee's request list. | Positive | `Attendance.Attendance.RequestEmergencyLeave` | `/LeavesManagement/EmergencyLeaves` | P0 | Not Run
UAT-008 | Leave | Regular employee | Leave balance | Open leave balances and verify own available/taken/remaining values. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/LeavesManagement/Balances`. 3. Execute scenario: Open leave balances and verify own available/taken/remaining values.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Employee can view allowed leave balance data without seeing unrelated employees unless permitted. | Positive | `Attendance.Attendance.ViewLeaveBalances` | `/LeavesManagement/Balances` | P0 | Not Run
UAT-009 | Leave | Regular employee | Leave validation | Submit leave with invalid date range, missing reason, or insufficient balance. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/LeavesManagement/EmergencyLeaves`. 3. Execute scenario: Submit leave with invalid date range, missing reason, or insufficient balance.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request is rejected; balance is not changed and clear validation is shown. | Negative | `Attendance.Attendance.RequestEmergencyLeave` | `/LeavesManagement/EmergencyLeaves` | P0 | Not Run
UAT-010 | Attendance | Regular employee | Mid-day permission | Submit a same-day permission request for a valid time window. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/Attendance/PermissionRequests`. 3. Execute scenario: Submit a same-day permission request for a valid time window.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request is submitted and appears with pending/review status. | Positive | `Attendance.Attendance.RequestMidDayPermission` | `/Attendance/PermissionRequests` | P0 | Not Run
UAT-011 | Task management | Regular employee | My tasks | Open My Tasks, view an assigned task, add a comment/progress update. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/TaskManagement/MyTasks`. 3. Execute scenario: Open My Tasks, view an assigned task, add a comment/progress update.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Only assigned/relevant tasks appear; comment/progress is saved in task history. | Positive | `TaskManagement.Task.View`, `TaskManagement.Task.Comment` | `/TaskManagement/MyTasks` | P0 | Not Run
UAT-012 | Task management | Regular employee | Task authorization | Try to edit, close, assign, or delete a task without those permissions. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Regular employee. 2. Navigate to `/TaskManagement/View/{id}`. 3. Execute scenario: Try to edit, close, assign, or delete a task without those permissions.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Restricted actions are hidden/disabled or rejected by backend. | Negative | Missing `Edit`, `Close`, `Assign`, or `Delete` | `/TaskManagement/View/{id}` | P0 | Not Run
UAT-013 | Task management | Department head | Create department task | Create a task for an employee in the same department and assign it. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Department head. 2. Navigate to `/TaskManagement/Create`. 3. Execute scenario: Create a task for an employee in the same department and assign it.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Task is created, assigned employee can see it, and notification appears where supported. | Positive | `TaskManagement.Task.Create`, `TaskManagement.Task.Assign` | `/TaskManagement/Create` | P0 | Not Run
UAT-014 | Task management | Department head | Department scope | Try assigning or viewing tasks for employees outside the department without manage-all permission. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Department head. 2. Navigate to `/TaskManagement/List`. 3. Execute scenario: Try assigning or viewing tasks for employees outside the department without manage-all permission.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Out-of-scope employee/task is unavailable or action is rejected. | Negative | Department head permissions without `ManageAllTasks` | `/TaskManagement/List` | P0 | Not Run
UAT-015 | Task management | Department head | Kanban/status | Move a department task through allowed statuses and close it. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Department head. 2. Navigate to `/TaskManagement/Kanban`. 3. Execute scenario: Move a department task through allowed statuses and close it.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Status updates persist; closed state is visible in list/detail/report views. | Positive | `TaskManagement.Task.View`, `TaskManagement.Task.Edit`, `TaskManagement.Task.Close` | `/TaskManagement/Kanban` | P0 | Not Run
UAT-016 | Leave | Department head | Approve emergency leave | Approve or reject a pending emergency leave for a subordinate. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Department head. 2. Navigate to `/LeavesManagement/ApproveEmergencyLeaves`. 3. Execute scenario: Approve or reject a pending emergency leave for a subordinate.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request status changes; employee sees the decision; balance impact follows business rules. | Positive | `Attendance.Attendance.ApproveEmergencyLeave` | `/LeavesManagement/ApproveEmergencyLeaves` | P0 | Not Run
UAT-017 | Attendance | Department head | Approve permission | Approve or reject a pending mid-day permission request. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Department head. 2. Navigate to `/Attendance/ApprovePermissionRequests`. 3. Execute scenario: Approve or reject a pending mid-day permission request.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request is reviewed and no longer appears as pending. | Positive | `Attendance.Attendance.ApproveMidDayPermission` | `/Attendance/ApprovePermissionRequests` | P0 | Not Run
UAT-018 | Reports | Department head | Scoped task/attendance reports | Open scoped reports and filter by date/department. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Department head. 2. Navigate to `/TaskManagement/Reports`, `/Attendance/Reports`. 3. Execute scenario: Open scoped reports and filter by date/department.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Reports show only allowed department scope and respect filters. | Positive | `TaskManagement.Task.ViewReports`, `Attendance.Attendance.ViewScopedReports` | `/TaskManagement/Reports`, `/Attendance/Reports` | P1 | Not Run
UAT-019 | Employee | HR admin | Employee CRUD | Create employee, edit core details, view employee profile/360, and validate list search. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as HR admin. 2. Navigate to `/Employee/Employee/List`. 3. Execute scenario: Create employee, edit core details, view employee profile/360, and validate list search.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Employee appears in list/profile and can be used by related modules. | Positive | `Employees.Employee.Create`, `View`, `Edit` | `/Employee/Employee/List` | P0 | Not Run
UAT-020 | Employee | HR admin | Employee validation | Create employee with missing required fields or duplicate identity/code where applicable. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as HR admin. 2. Navigate to `/Employee/Employee/Form/{id?}`. 3. Execute scenario: Create employee with missing required fields or duplicate identity/code where applicable.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Save is blocked; no partial employee is created. | Negative | `Employees.Employee.Create` | `/Employee/Employee/Form/{id?}` | P1 | Not Run
UAT-021 | Attendance | HR admin | Shifts and assignments | Create/update shift and assign to employee/department. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as HR admin. 2. Navigate to `/Attendance/Shifts`, `/Attendance/ShiftAssignments`. 3. Execute scenario: Create/update shift and assign to employee/department.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Shift and assignment save; attendance pages use updated schedule. | Positive | `Attendance.Attendance.Edit` | `/Attendance/Shifts`, `/Attendance/ShiftAssignments` | P0 | Not Run
UAT-022 | Attendance | HR admin | Attendance sessions review | Review late check-in/session normalization request. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as HR admin. 2. Navigate to `/Attendance/Sessions`, `/Attendance/LateRequests`. 3. Execute scenario: Review late check-in/session normalization request.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request/session review decision is saved and reflected in reports. | Positive | `Attendance.Attendance.ReviewRequests` | `/Attendance/Sessions`, `/Attendance/LateRequests` | P0 | Not Run
UAT-023 | Attendance | HR admin | Configuration and holidays | Update break policy/configuration and add holiday/weekend entry. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as HR admin. 2. Navigate to `/Attendance/Configuration`, `/Attendance/Holidays`. 3. Execute scenario: Update break policy/configuration and add holiday/weekend entry.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Configuration persists and affects relevant validation/reporting behavior. | Positive | `ViewConfiguration`, `ManageConfiguration`, `ManageHolidays` | `/Attendance/Configuration`, `/Attendance/Holidays` | P1 | Not Run
UAT-024 | Leave | HR admin | Leave balance management | Adjust or configure employee leave balance. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as HR admin. 2. Navigate to `/LeavesManagement/Balances`. 3. Execute scenario: Adjust or configure employee leave balance.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Balance changes persist with correct available/taken/remaining calculation. | Positive | `Attendance.Attendance.ManageLeaveBalances` | `/LeavesManagement/Balances` | P0 | Not Run
UAT-025 | Payroll | Payroll user/head | Salary contracts | Create/edit salary contract and assign it to an employee. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Payroll user/head. 2. Navigate to `/Payroll/Contracts`, `/Payroll/AssignContract`. 3. Execute scenario: Create/edit salary contract and assign it to an employee.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Contract is saved and employee assignment is visible for payroll runs. | Positive | `Payroll.Contract.Create`, `Edit`, `View` | `/Payroll/Contracts`, `/Payroll/AssignContract` | P1 | Not Run
UAT-026 | Payroll | Payroll user/head | Contract validation | Save contract with missing employee/component/date or invalid amount. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Payroll user/head. 2. Navigate to `/Payroll/Contracts`. 3. Execute scenario: Save contract with missing employee/component/date or invalid amount.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Validation prevents save; no incorrect payroll contract is used. | Negative | `Payroll.Contract.Create` | `/Payroll/Contracts` | P1 | Not Run
UAT-027 | Payroll | Payroll user/head | Employee loans | Create, approve, and cancel a loan according to status rules. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Payroll user/head. 2. Navigate to `/Payroll/Loans`. 3. Execute scenario: Create, approve, and cancel a loan according to status rules.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Loan status changes correctly and cannot be edited in invalid states. | Positive | `Payroll.Loan.Create`, `Edit`, `Approve`, `Cancel` | `/Payroll/Loans` | P1 | Not Run
UAT-028 | Payroll | Payroll user/head | Salary run | Generate salary run for a valid period and approve it. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Payroll user/head. 2. Navigate to `/Payroll/SalaryRuns`. 3. Execute scenario: Generate salary run for a valid period and approve it.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Salary run is created with employees, totals, and approved status. | Positive | `Payroll.SalaryRun.Create`, `View`, `Approve` | `/Payroll/SalaryRuns` | P0 | Not Run
UAT-029 | Payroll | Payroll user/head | Salary run control | Attempt duplicate generation or undo without admin override. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Payroll user/head. 2. Navigate to `/Payroll/SalaryRuns`. 3. Execute scenario: Attempt duplicate generation or undo without admin override.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Duplicate/unauthorized operation is rejected; existing run remains intact. | Negative | Missing `AdminOverride` or duplicate period | `/Payroll/SalaryRuns` | P0 | Not Run
UAT-030 | Customers | Sales personnel | Customer maintenance | Create/edit a customer and assign group/pricing profile where available. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Sales personnel. 2. Navigate to `/Customers/Customer/List`. 3. Execute scenario: Create/edit a customer and assign group/pricing profile where available.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Customer is saved and selectable in sales/POS flows. | Positive | `Customers.Customer.Create`, `Edit`, `View` | `/Customers/Customer/List` | P1 | Not Run
UAT-031 | Sales | Sales personnel | POS/sales order create | Create a POS/order using valid customer, product SKU, pricing, and stock. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Sales personnel. 2. Navigate to `/SalesOrder/POS`. 3. Execute scenario: Create a POS/order using valid customer, product SKU, pricing, and stock.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Order/cart is saved; totals calculate; inventory/pricing data is used. | Positive | `SalesOrders.Order.Create`, product/variant/inventory view permissions | `/SalesOrder/POS` | P0 | Not Run
UAT-032 | Sales | Sales personnel | Sales validation | Attempt order with unavailable stock, missing customer/product, or invalid quantity. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Sales personnel. 2. Navigate to `/SalesOrder/POS`. 3. Execute scenario: Attempt order with unavailable stock, missing customer/product, or invalid quantity.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Order is blocked or line is rejected; stock and totals remain unchanged. | Negative | `SalesOrders.Order.Create` | `/SalesOrder/POS` | P0 | Not Run
UAT-033 | Sales | Sales head | Order lifecycle | Confirm, deliver, invoice, complete an eligible order. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Sales head. 2. Navigate to Sales order/POS/order views. 3. Execute scenario: Confirm, deliver, invoice, complete an eligible order.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Order moves through expected lifecycle and final status is visible. | Positive | `SalesOrders.Order.Confirm`, `Deliver`, `Invoice`, `Complete` | Sales order/POS/order views | P0 | Not Run
UAT-034 | Sales | Sales head | Sales lifecycle control | Try invoice before delivery, complete cancelled order, or return without allowed state. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Sales head. 2. Navigate to Sales order/POS/order views. 3. Execute scenario: Try invoice before delivery, complete cancelled order, or return without allowed state.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Invalid state transition is rejected; audit/status remains correct. | Negative | Sales lifecycle permissions | Sales order/POS/order views | P0 | Not Run
UAT-035 | Payments | Sales head | Payment approval/refund | Approve/reject payment and process refund where available. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Sales head. 2. Navigate to Payment-related sales route/API. 3. Execute scenario: Approve/reject payment and process refund where available.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Payment status updates and order financial state reflects the decision. | Positive | `Payments.Payment.Approve`, `Reject`, `Refund` | Payment-related sales route/API | P1 | Not Run
UAT-036 | Procurement | Procurement user/head | Purchase request | Create purchase request, submit it, approve/reject it. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Procurement user/head. 2. Navigate to `/Procurement/purchase-requests`. 3. Execute scenario: Create purchase request, submit it, approve/reject it.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Request status changes through draft/submitted/approved or rejected. | Positive | `Procurement.PurchaseRequest.Create`, `Submit`, `Approve`, `Reject` | `/Procurement/purchase-requests` | P0 | Not Run
UAT-037 | Procurement | Procurement user/head | RFQ | Create RFQ from valid data and send/close/cancel it. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Procurement user/head. 2. Navigate to `/Procurement/requests-for-quotation`. 3. Execute scenario: Create RFQ from valid data and send/close/cancel it.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | RFQ is saved and workflow action updates status. | Positive | `Procurement.RequestForQuotation.Create`, `Submit`, `Close`, `Cancel` | `/Procurement/requests-for-quotation` | P0 | Not Run
UAT-038 | Procurement | Procurement user/head | Supplier quotation | Create supplier quotation and accept/reject it. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Procurement user/head. 2. Navigate to `/Procurement/supplier-quotations`. 3. Execute scenario: Create supplier quotation and accept/reject it.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Accepted quotation can feed the next procurement step where supported. | Positive | `Procurement.SupplierQuotation.Create`, `Approve`, `Reject` | `/Procurement/supplier-quotations` | P0 | Not Run
UAT-039 | Procurement | Procurement user/head | Purchase order | Create/send/approve/cancel/close purchase order. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Procurement user/head. 2. Navigate to `/Procurement/purchase-orders`. 3. Execute scenario: Create/send/approve/cancel/close purchase order.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Purchase order status and downstream availability update correctly. | Positive | `Procurement.PurchaseOrder.Create`, `Submit`, `Approve`, `Cancel`, `Close` | `/Procurement/purchase-orders` | P0 | Not Run
UAT-040 | Procurement | Procurement user/head | Receiving and invoice | Post goods receipt, create supplier invoice, match/post/cancel invoice. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Procurement user/head. 2. Navigate to `/Procurement/goods-receipts`, `/Procurement/supplier-invoices`. 3. Execute scenario: Post goods receipt, create supplier invoice, match/post/cancel invoice.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Inventory/receiving and invoice statuses update consistently. | Positive | `GoodsReceipt.Receive`, `SupplierInvoice.Approve`, `SupplierInvoice.Close`, `SupplierInvoice.Cancel` | `/Procurement/goods-receipts`, `/Procurement/supplier-invoices` | P0 | Not Run
UAT-041 | Procurement | Procurement user/head | Procurement validation | Try approving draft, posting cancelled document, or editing closed document. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Procurement user/head. 2. Navigate to `/Procurement/{kind}`. 3. Execute scenario: Try approving draft, posting cancelled document, or editing closed document.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Invalid workflow state is rejected; document remains unchanged. | Negative | Relevant procurement permissions | `/Procurement/{kind}` | P0 | Not Run
UAT-042 | Catalog | Inventory/catalog user | Product master data | Create category, brand, unit, variant, product, SKU, and package. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Inventory/catalog user. 2. Navigate to Catalog/product routes. 3. Execute scenario: Create category, brand, unit, variant, product, SKU, and package.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Master data is saved and selectable by inventory, sales, and procurement flows. | Positive | Relevant `Catalog.*` create/edit/view permissions | Catalog/product routes | P1 | Not Run
UAT-043 | Catalog | Inventory/catalog user | Catalog validation | Create duplicate or incomplete master data record. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Inventory/catalog user. 2. Navigate to Catalog/product routes. 3. Execute scenario: Create duplicate or incomplete master data record.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Save is blocked or duplicate is rejected according to validation rules. | Negative | Relevant `Catalog.*.Create` | Catalog/product routes | P1 | Not Run
UAT-044 | Pricing | Inventory/catalog user | Price list | Create/edit a price list for products/SKUs. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Inventory/catalog user. 2. Navigate to `/Catalog/Pricing/List`. 3. Execute scenario: Create/edit a price list for products/SKUs.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Price list is visible and sales/POS pricing reflects expected value. | Positive | `Pricing.PriceList.Create`, `Edit`, `View` | `/Catalog/Pricing/List` | P1 | Not Run
UAT-045 | Inventory | Inventory/catalog user | Warehouse and batches | Create warehouse and batch, then verify current stock page. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Inventory/catalog user. 2. Navigate to `/Inventory/Warehouse/List`, `/Inventory/Batch/List`, `/Inventories/List`. 3. Execute scenario: Create warehouse and batch, then verify current stock page.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Warehouse/batch records save and appear in inventory selection/list views. | Positive | `Inventory.Warehouse.*`, `Inventory.Batch.*`, `Inventory.Inventory.View` | `/Inventory/Warehouse/List`, `/Inventory/Batch/List`, `/Inventories/List` | P1 | Not Run
UAT-046 | Inventory | Inventory/catalog user | Stock operations | Perform stock in, stock out, adjustment, reserve, and release. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Inventory/catalog user. 2. Navigate to `/Inventory/Operations/StockIn`, `/StockOut`, `/StockAdjustment`, `/StockReservation`, `/StockRelease`. 3. Execute scenario: Perform stock in, stock out, adjustment, reserve, and release.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Stock quantities, reservations, and availability update correctly. | Positive | `Inventory.Inventory.Create/Edit`, `Inventory.InventoryItem.Create/Edit` | `/Inventory/Operations/StockIn`, `/StockOut`, `/StockAdjustment`, `/StockReservation`, `/StockRelease` | P0 | Not Run
UAT-047 | Inventory | Inventory/catalog user | Stock validation | Try stock out more than available or release more than reserved. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Inventory/catalog user. 2. Navigate to Inventory operation routes. 3. Execute scenario: Try stock out more than available or release more than reserved.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Operation is rejected; stock quantities remain unchanged. | Negative | Inventory operation permissions | Inventory operation routes | P0 | Not Run
UAT-048 | Security | System admin | Role management | Create role, select permissions, edit role, and verify grouped permission list. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as System admin. 2. Navigate to `/Auth/Role/List`, `/Auth/Role/Form`. 3. Execute scenario: Create role, select permissions, edit role, and verify grouped permission list.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Role is saved with selected permission claims and can be assigned. | Positive | `Authentication.Roles.Create`, `View`, `Edit` | `/Auth/Role/List`, `/Auth/Role/Form` | P0 | Not Run
UAT-049 | Security | System admin | User role assignment | Assign and unassign role for a test user, then log in as that user. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as System admin. 2. Navigate to `/Auth/User/AssignRole`. 3. Execute scenario: Assign and unassign role for a test user, then log in as that user.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | User menu/actions change according to assigned role after login/session refresh. | Positive | `Authentication.Users.View`, `Authentication.Roles.Create/Delete` | `/Auth/User/AssignRole` | P0 | Not Run
UAT-050 | Organization | System admin | Organization setup | Create/edit branch, administration, and department. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as System admin. 2. Navigate to Organization routes. 3. Execute scenario: Create/edit branch, administration, and department.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Structure saves and becomes available for employee assignment and scoped reports. | Positive | `Organization.Branch.*`, `Organization.Administration.*`, `Organization.Department.*` | Organization routes | P1 | Not Run
UAT-051 | Organization | System admin | Child company controls | View/create/edit/disable child company and reset child admin password where available. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as System admin. 2. Navigate to `/Organization/ChildCompanies`. 3. Execute scenario: View/create/edit/disable child company and reset child admin password where available.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Child company operation completes and status/admin access changes as expected. | Positive | `Organization.Company.ViewChild`, `CreateChild`, `EditChild`, `DisableChild`, `ResetChildAdminPassword` | `/Organization/ChildCompanies` | P1 | Not Run
UAT-052 | General settings | System admin | System settings/currencies | View/edit system settings and currencies. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as System admin. 2. Navigate to `/GeneralSettings/SystemSettings`, `/GeneralSettings/Currencies`. 3. Execute scenario: View/edit system settings and currencies.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Setting/currency changes persist and are reflected in dependent UI where applicable. | Positive | `GeneralSettings.SystemSettings.View`, `Edit` | `/GeneralSettings/SystemSettings`, `/GeneralSettings/Currencies` | P2 | Not Run
UAT-053 | Lists and search | All roles | Lists | Search, filter, paginate, open empty-state list, and verify loading/error handling on allowed pages. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as All roles. 2. Navigate to Any list route. 3. Execute scenario: Search, filter, paginate, open empty-state list, and verify loading/error handling on allowed pages.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Lists remain usable; filters/paging work; empty/error states are understandable. | Positive | Relevant `View` permission | Any list route | P2 | Not Run
UAT-054 | Reports | Reporting roles | Reports | Run attendance, leave, task, sales, procurement, and inventory reports where available. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as Reporting roles. 2. Navigate to Report routes. 3. Execute scenario: Run attendance, leave, task, sales, procurement, and inventory reports where available.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | Reports respect filters, user scope, and show/export expected data where supported. | Positive | Relevant `ViewReports`, `ViewScopedReports`, or `ViewAllReports` | Report routes | P2 | Not Run
UAT-055 | API/security | All roles | Direct action control | Use browser/dev tools or direct API client to call an action without the required permission. | Use global prerequisites and role-specific permissions from the Role Matrix sheet. Confirm required seed data exists before execution. | 1. Sign in as All roles. 2. Navigate to Relevant API endpoint. 3. Execute scenario: Use browser/dev tools or direct API client to call an action without the required permission.. 4. Capture result and evidence. | Use test company/branch/department data and existing seed/master data matching the scenario. | API returns unauthorized/forbidden; no data is changed. | Negative | Missing action permission | Relevant API endpoint | P0 | Not Run

## Role Matrix
Test role | Minimum permissions to assign
Regular employee | `Attendance.Attendance.Create`, `Attendance.Attendance.RequestEmergencyLeave`, `Attendance.Attendance.RequestMidDayPermission`, `Attendance.Attendance.ViewLeaveBalances`, `TaskManagement.Task.View`, `TaskManagement.Task.Comment`
Department head | Regular employee permissions plus `TaskManagement.Task.Create`, `TaskManagement.Task.Assign`, `TaskManagement.Task.Edit`, `TaskManagement.Task.Close`, `TaskManagement.Task.ViewReports`, `Attendance.Attendance.ApproveEmergencyLeave`, `Attendance.Attendance.ApproveMidDayPermission`, `Attendance.Attendance.ViewScopedReports`
HR/attendance admin | `Employees.Employee.*`, `Employees.Position.*`, `Attendance.Attendance.Select`, `Attendance.Attendance.View`, `Attendance.Attendance.Edit`, `Attendance.Attendance.ReviewRequests`, `Attendance.Attendance.ViewConfiguration`, `Attendance.Attendance.ManageConfiguration`, `Attendance.Attendance.ManageHolidays`, `Attendance.Attendance.ViewLeaveBalances`, `Attendance.Attendance.ManageLeaveBalances`, `Attendance.Attendance.ViewReports`, `Attendance.Attendance.ViewAllReports`
Payroll user/head | `Payroll.Contract.Select`, `Payroll.Contract.View`, `Payroll.Contract.Create`, `Payroll.Contract.Edit`, `Payroll.Loan.Select`, `Payroll.Loan.View`, `Payroll.Loan.Create`, `Payroll.Loan.Edit`, `Payroll.Loan.Approve`, `Payroll.Loan.Cancel`, `Payroll.SalaryRun.Select`, `Payroll.SalaryRun.View`, `Payroll.SalaryRun.Create`, `Payroll.SalaryRun.Edit`, `Payroll.SalaryRun.Approve`, `Payroll.SalaryRun.AdminOverride`
Sales personnel | `Customers.Customer.Select`, `Customers.Customer.View`, `Customers.Customer.Create`, `Customers.Customer.Edit`, `Catalog.Product.View`, `Catalog.Variant.View`, `Inventory.Inventory.View`, `SalesOrders.Order.Select`, `SalesOrders.Order.View`, `SalesOrders.Order.Create`, `Cart.Cart.*` where POS/cart actions are enabled
Sales head/approver | Sales personnel permissions plus `SalesOrders.Order.Edit`, `SalesOrders.Order.Confirm`, `SalesOrders.Order.Deliver`, `SalesOrders.Order.Invoice`, `SalesOrders.Order.Complete`, `SalesOrders.Order.Cancel`, `SalesOrders.Order.Return`, `SalesOrders.Order.ViewReports`, `Payments.Payment.Approve`, `Payments.Payment.Reject`, `Payments.Payment.Refund`
Procurement user/head | `Procurement.PurchaseRequest.*`, `Procurement.RequestForQuotation.*`, `Procurement.SupplierQuotation.*`, `Procurement.PurchaseOrder.*`, `Procurement.GoodsReceipt.*`, `Procurement.PurchaseReturn.*`, `Procurement.SupplierInvoice.*`, `Suppliers.Supplier.View`, `Catalog.Product.View`, `Inventory.Warehouse.View`
Inventory/catalog user | `Catalog.Category.*`, `Catalog.Brand.*`, `Catalog.Unit.*`, `Catalog.Variant.*`, `Catalog.Product.*`, `Catalog.ProductPackage.*`, `Pricing.PriceList.*`, `Inventory.Warehouse.*`, `Inventory.Batch.*`, `Inventory.Inventory.*`, `Inventory.InventoryItem.*`
System admin | `Authentication.Users.*`, `Authentication.Roles.*`, `Organization.Company.*`, `Organization.Branch.*`, `Organization.Administration.*`, `Organization.Department.*`, `GeneralSettings.SystemSettings.*`

## Execution Guide
Manual UAT Execution Guide | Manual UAT Execution Guide | Manual UAT Execution Guide | Manual UAT Execution Guide
Topic | Guidance | Applies to | Evidence
Prerequisites | Confirm environment, users, permissions, and master data before testing. | All cases | Setup screenshot or notes
Priority | Execute P0 first, then P1, then P2. | All cases | Tracker status
Positive cases | Confirm the operation succeeds and expected downstream state is visible. | Positive rows | Record ID and screenshot
Negative cases | Confirm the operation fails safely and no data is changed. | Negative rows | Error screenshot plus before/after state
Permissions | Verify both menu/action visibility and direct backend authorization where practical. | Security-sensitive rows | Route/API result
Scope | For department/company tests, compare in-scope and out-of-scope data. | Scoped rows | Filtered report/list screenshot
Localization | Check English/Arabic text direction and action alignment. | Cross-cutting rows | Before/after screenshot
Defects | Log defect ID when Actual Result differs from Expected Result. | Failed rows | Defect ID/link
Retest | Retest changed workflows after role, permission, or seed-data fixes. | Failed/blocked rows | Updated status