# AlafkarERP Full-System Implementation Plan

## Purpose

This plan guides a company rollout of the full Alafkar ERP platform from preparation through post-go-live support. It is written for company leadership, finance, sales, procurement, warehouse, HR, payroll, operations, business-line owners, IT, implementation consultants and key users.

The implementation scope is not HR-only. It covers HR plus the confirmed ERP modules, workspaces and business lines found in the repository.

## Confirmed Full-System Capability Map

| Domain | Confirmed capabilities |
| --- | --- |
| Organization and business lines | Company, parent/child company context, branches, administrations, departments, business lines, license categories, branch access and business-line activation. |
| Security | Users, roles, role assignment, permission groups, company-scoped roles, branch access permissions, scoped StoreFront branch roles and security dashboard. |
| Accounting and finance | Accounting setup, templates, chart of accounts, fiscal periods, tax codes, posting profiles, bank/cash accounts, journals, documents, sales invoices, purchase invoices, receipts/payments, credit notes, debit notes, bank reconciliation, finance reports, ZATCA submissions and ZATCA settings. |
| Sales and orders | Sales dashboard, quotations, order intake, sales orders, delivery notes, returns and sales workflow validation. |
| Customers and pricing | Customer dashboard, customer records, customer groups, customer pricing profiles, catalog pricing and commercial master data. |
| Procurement and purchasing | Procurement dashboard, procurement documents, forms, detail views, tracker, vendor pricelists, supplier items, supplier scorecard, reordering rules and procurement enhancements. |
| Suppliers | Supplier list, supplier form, supplier view and supplier groups. |
| Catalog, warehouse and inventory | Product dashboard, product records, SKUs, categories, brands, units, variants, packages, price lists, warehouses, inventory records, batches, asset instances, movements, transfers, controls, stock-in, stock-out, stock adjustment, stock reservation and stock release. |
| StoreFront and POS | POS workspace, stores, departments, StoreFront organization and store management for the store-front business line. |
| Catering | Catering dashboard, contracts, meals, locations, schedules, deliveries, assignments and reports for the catering business line. |
| Real Estate | Real estate dashboard, properties, units, owner leases, tenant leases, collections, utilities, expenses and reports for the real-estate business line. |
| Contracts | Contract dashboard, contract list, forms, detail views, renewals, templates and party-specific contract views. |
| Document Management and Media Center | Document list, create, view, my documents, shared documents, source documents, upload policy, media activities, media activity detail and activity types. |
| Projects and tasks | Project dashboard, projects, distribution places, distribution schedules, project reports, task dashboard, my tasks, notifications, task list, kanban, task reports, task create/edit/view. |
| Fleet | Fleet dashboard, vehicles, assignments, expenses, documents, service rules and reports. |
| Maintenance | Maintenance dashboard, assets, work orders, my maintenance requests and reports. |
| Payments | Payment-related setup and transaction support that must be validated with finance and operations owners. |
| Employees | Employee records, company/branch/administration/department/position filters, employee view, public view, QR view, 360 view, teams, positions, academic institutions, specializations. |
| Employee enhancements | Lifecycle events, emergency contacts, document links, skills, certifications, command center, HR reports. |
| Attendance | Dashboard, my attendance, attendance sessions, check-in preview, shifts, shift assignment, holidays, late check-in requests, mid-day permission requests, approvals, reports. |
| Roster and work entries | Roster controls, substitute configuration, shift schedules, shift schedule assignments, shift swaps, corrections, biometric import batches, payroll work entries. |
| Leave | Emergency leave, leave balances, leave reports, leave types, periods, policies, assignments, allocations, leave applications, leave ledger, adjustments, encashment. |
| Payroll | Components, contracts, employee contract assignment, salary runs, period commit/undo, employee loans, salary structures, payroll periods, payroll entries, payslips, payroll inputs, Saudi payroll info, WPS batches, EOS provision snapshots, payroll accounting posting, work-entry import. |
| Recruitment | Staffing plans, job requisitions, applicants, interview feedback, offers, offer-to-employee marking. Requires business validation for final approval rules. |
| Performance | Appraisal cycles, goals, competencies, employee goals, competency scores, evaluations, submit/review/approve/cancel flow. Requires business validation for scoring policy. |
| Training | Training programs, events, attendees, attendance, results, certificate links. Requires business validation for training governance. |
| General settings | System settings, home page templates, currencies. |

## Implementation Goals

Establish accurate organization, branch, business-line and security foundations.

Configure accounting, tax, ZATCA, fiscal, bank/cash and posting setup before transaction testing.

Prepare commercial master data: customers, suppliers, products, SKUs, pricing, warehouses and opening inventory.

Enable daily ERP operations across sales, procurement, warehouse, POS, contracts, projects, tasks, fleet, maintenance and payments.

Implement confirmed business lines: catering, real-estate and store-front.

Migrate and validate employee, HR, attendance, leave and payroll data.

Configure permission-safe access by company, branch, workspace and business-line role.

Train each role with the role-based guides in this package.

Complete controlled go-live with sign-offs, support ownership and post-go-live review.

## Implementation Assumptions

| Assumption | Validation owner |
| --- | --- |
| The company has an approved organization, branch and department structure before configuration starts. | Project Sponsor |
| Business-line activation for catering, real-estate and store-front is approved before UAT. | System Owner |
| Accounting templates, chart of accounts, fiscal periods, tax/ZATCA rules, posting profiles and bank/cash accounts are approved before transactional testing. | Finance Lead |
| Customer, supplier, product, SKU, pricing, warehouse and opening-stock source data can be provided in a clean spreadsheet format. | Commercial and Warehouse Data Owners |
| Sales, procurement, POS, contract, project, fleet and maintenance workflows are approved by functional owners before UAT. | Operations Lead |
| Employee source data can be exported to spreadsheet format. | HR Data Owner |
| Payroll rules, components, periods, WPS requirements, and Saudi payroll fields are approved before payroll setup. | Payroll Lead |
| Attendance devices, geolocation rules, shifts, and holiday calendars are agreed before attendance UAT. | Attendance Lead |
| User roles, branch access and business-line visibility rules are approved before UAT. | IT Security Lead |
| Arabic and English terminology is reviewed by business owners before training. | Functional Leads |

## Phase Plan

| Phase | Duration | Main activities | Key deliverables |
| --- | --- | --- | --- |
| 1. Mobilization | Week 1 | Kickoff, governance, stakeholder confirmation, project workspace, document sign-off process. | Project charter, RACI, timeline, issue log. |
| 2. Full-System Discovery and Fit | Weeks 1-2 | Confirm organization, security, finance, sales, procurement, inventory, POS, HR, payroll, business-line and operational workflows. | Scope of work, workflow mapping, module catalog, validation register. |
| 3. Data Preparation | Weeks 2-4 | Collect organization, finance, customer, supplier, catalog, inventory, HR, payroll, POS, catering, real estate, contract, project, fleet and maintenance data. | Master data templates, migration plan, cleansing tracker. |
| 4. Foundation Configuration | Weeks 3-5 | Configure organization, business lines, roles, users, settings, currencies, chart of accounts, fiscal periods, tax, ZATCA, branches and accounting templates. | Configured foundation, access matrix, finance setup sign-off. |
| 5. Operational Configuration | Weeks 4-7 | Configure commercial, procurement, warehouse, catalog, pricing, POS, contracts, documents, projects, tasks, fleet, maintenance, HR, attendance, leave and payroll masters. | Configuration workbook, module readiness evidence. |
| 6. Migration and Reconciliation | Weeks 5-8 | Load or enter data, reconcile counts, validate opening balances, validate employee records, prepare attachments and identifiers. | Migration reconciliation, exception log, data sign-off. |
| 7. Testing | Weeks 6-9 | SIT, UAT, role-based workflows, finance posting checks, inventory movement checks, POS scenarios, payroll parallel run if payroll is in scope and security testing. | Test plan results, UAT sign-off. |
| 8. Training and Change | Weeks 8-10 | Train administrators, finance, sales, procurement, warehouse, POS, business-line users, HR, payroll, managers, employees and specialist roles. | Training attendance, quick references, readiness report. |
| 9. Cutover and Go-Live | Week 11 | Freeze source changes, final migration, final validation, enable users, go-live communications. | Cutover checklist, go-live sign-off. |
| 10. Hypercare | Weeks 11-13 | Daily triage, issue resolution, adoption support, report reconciliation and handover to support. | Hypercare log, support handover, post-go-live review. |

## Workstreams

| Workstream | Scope |
| --- | --- |
| Governance | Kickoff, steering committee, status reporting, decisions, risks, issues, change requests. |
| Organization, Business Lines and Security | Company setup, branches, departments, administrations, business lines, roles, users, permission assignment, branch access and StoreFront branch roles. |
| Accounting and Finance | Accounts, fiscal periods, taxes, posting profiles, bank/cash accounts, journals, invoices, payments, reconciliation, ZATCA and finance reporting. |
| Sales and Customers | Customers, groups, pricing profiles, quotations, order intake, sales orders, delivery notes and returns. |
| Procurement and Suppliers | Suppliers, supplier groups, procurement documents, vendor prices, supplier items, scorecards and reordering rules. |
| Catalog, Pricing, Warehouse and Inventory | Products, SKUs, categories, brands, units, variants, packages, price lists, warehouses, batches, assets, movements, transfers and stock operations. |
| POS and StoreFront | StoreFront organization, stores, departments, POS operation, cashier readiness and daily reconciliation. |
| Catering | Contracts, meals, locations, schedules, deliveries, assignments and catering reports. |
| Real Estate | Properties, units, owner leases, tenant leases, collections, utilities, expenses and real estate reports. |
| Contracts, Documents and Media | Contract templates and renewals, document upload and visibility, source documents, media activities and activity types. |
| Projects, Tasks, Fleet and Maintenance | Project setup, distribution schedules, task assignment, kanban, fleet vehicles/assignments/expenses/documents/service rules, maintenance assets and work orders. |
| HR Core | Employees, positions, teams, academic institutions, specializations, lifecycle, documents, skills, certifications. |
| Attendance | Shifts, sessions, check-in rules, holidays, late requests, mid-day permissions, roster, corrections, biometric import. |
| Leave | Leave types, periods, policies, balances, applications, emergency leave, ledger, reports. |
| Payroll | Components, contracts, salary structures, periods, payroll entries, payslips, loans, WPS, Saudi payroll, accounting posting. |
| Talent | Recruitment, performance, and training workflows. |
| Data | Templates, cleansing, migration, reconciliation, attachment tracking. |
| Testing and Training | SIT, UAT, training, role guides, readiness. |
| Go-Live and Support | Cutover, communications, hypercare, support transition. |

## Business Lines and Workspace Rollout

| Business line or workspace | Rollout focus | Success condition |
| --- | --- | --- |
| catering | Catering contracts, meals, service locations, schedules, deliveries, assignments and reports. | Catering users can execute and report daily service operations. |
| real-estate | Properties, units, owner leases, tenant leases, collections, utilities, expenses and reports. | Property users can manage leases, collections and operating expenses. |
| store-front | StoreFront organization, stores, departments, POS, cashier access and store management. | Store users can operate POS and reconcile daily sales with finance. |
| Accounting/Finance | Finance setup, journals, invoices, payments, bank/cash, ZATCA and reports. | Finance owner signs off posting, tax, reconciliation and reporting scenarios. |
| Sales | Customer setup, quotations, orders, delivery notes and returns. | Sales owner signs off quote-to-order-to-delivery scenarios. |
| Purchasing | Supplier setup, procurement documents, vendor prices and reordering. | Procurement owner signs off purchase lifecycle and supplier controls. |
| Warehouse | Catalog, pricing, inventory, transfers, stock operations and controls. | Warehouse owner signs off stock accuracy, movement and adjustment scenarios. |
| HR | Employees, attendance, leave, payroll, recruitment, performance and training. | HR/payroll owners sign off employee lifecycle and payroll scenarios. |
| Admin/Security | Users, roles, permissions, branches, business-line visibility and settings. | Security owner signs off access matrix and branch/business-line visibility. |

## Success Criteria

Full ERP scope is confirmed and signed off, including HR and all operational, finance and business-line modules.

Organization, branch, department and business-line structures match approved company records.

Accounting, tax, fiscal, posting, bank/cash and ZATCA setup is approved by finance.

Customers, suppliers, products, SKUs, pricing, warehouses and opening inventory are reconciled.

Sales, procurement, inventory, POS, catering, real estate, contracts, documents, projects, tasks, fleet and maintenance UAT scenarios are completed successfully.

100% of approved active employees are available in AlafkarERP.

Role-based access is approved and tested for each workspace and business line.

Critical UAT defects are closed or formally accepted before go-live.

End users complete training or receive approved reference material.

Hypercare triage process is active from the first business day after go-live.

## Business Validation Required

Accounting policies, chart of accounts, posting profiles, fiscal periods, tax treatment, ZATCA setup, invoice rules, receipts/payments and bank reconciliation.

Sales quotation, discount, customer pricing, delivery, return and credit policies.

Procurement approval thresholds, supplier onboarding, vendor price rules, scorecards and reordering policy.

Product coding, SKU, unit, warehouse, opening stock, costing, reservation, transfer and adjustment rules.

POS cashier control, payment methods, refund policy, store reconciliation and branch-role scope.

Catering contract terms, meal plans, delivery proof, schedule exceptions and billing triggers.

Real estate lease templates, rent schedules, utility recovery, owner settlement, expense allocation and legal terms.

Contract approval chains, renewal rules, templates and document retention.

Project/task ownership, reporting cadence, fleet assignment, service thresholds, maintenance work-order escalation and asset policies.

Final payroll calculations, allowances, deductions, EOS, WPS, and accounting posting policy.

Attendance geolocation, biometric import format, late check-in, mid-day permission, correction, and roster approval rules.

Leave accrual, carry-forward, encashment, emergency leave, attachment, and approval rules.

Recruitment approval thresholds, offer approval, and employee creation policy.

Performance rating scales, appraisal cycles, manager review, and approval authority.

Training attendance, result recording, certification, and completion rules.