Implementation Handbook

AlafkarHR Company Rollout

Implementation plan, templates, test pack, go-live controls, and role-based user guides

| Prepared for | Company implementation team, HR, IT, payroll, managers, and end users |
| --- | --- |
| Source package | docs/implementation/alafkarhr-company-rollout |
| Format | Editable Microsoft Word document with Word-native headings and TOC field |
| Status | Generated from repository documentation package |

# Table of Contents

Right-click and update field to refresh page numbers.

Tip: in Word, right-click the table above and choose Update Field to refresh page numbers. The chapter list below is immediately readable.

## Chapter List

Chapter 1: AlafkarHR Implementation Plan

Chapter 2: Project Charter

Chapter 3: Scope of Work

Chapter 4: Stakeholder Register

Chapter 5: RACI Matrix

Chapter 6: Data Migration Plan

Chapter 7: Master Data Collection Template

Chapter 8: Employee Data Collection Template

Chapter 9: Configuration Workbook

Chapter 10: Roles and Permissions Matrix

Chapter 11: Workflow Mapping

Chapter 12: Test Plan

Chapter 13: UAT Test Scripts

Chapter 14: Training Plan

Chapter 15: Communication and Change Management Plan

Chapter 16: Go-Live Checklist

Chapter 17: Cutover Plan

Chapter 18: Support and Hypercare Plan

Chapter 19: Risk and Issue Register

Chapter 20: Sign-Off Templates

Chapter 21: Post-Go-Live Review

Chapter 22: User Guide: System Administrator

Chapter 23: User Guide: HR Administrator

Chapter 24: User Guide: Employee

Chapter 25: User Guide: Manager and Supervisor

Chapter 26: User Guide: Payroll Officer

Chapter 27: User Guide: Specialist Roles

Appendix: Documentation Index

# Chapter 1: AlafkarHR Implementation Plan

## Purpose

This plan guides a company rollout of AlafkarHR from preparation through post-go-live support. It is written for company leadership, HR, payroll, IT, implementation consultants, and key users.

## Confirmed System Capability Map

| Domain | Confirmed capabilities |
| --- | --- |
| Organization | Company, parent/child company context, branches, administrations, departments, business lines, license categories, branch access. |
| Security | Users, roles, role assignment, permission groups, company-scoped roles, branch access permissions, security dashboard. |
| Employees | Employee records, company/branch/administration/department/position filters, employee view, public view, QR view, 360 view, teams, positions, academic institutions, specializations. |
| Employee enhancements | Lifecycle events, emergency contacts, document links, skills, certifications, command center, HR reports. |
| Attendance | Dashboard, my attendance, attendance sessions, check-in preview, shifts, shift assignment, holidays, late check-in requests, mid-day permission requests, approvals, reports. |
| Roster and work entries | Roster controls, substitute configuration, shift schedules, shift schedule assignments, shift swaps, corrections, biometric import batches, payroll work entries. |
| Leave | Emergency leave, leave balances, leave reports, leave types, periods, policies, assignments, allocations, leave applications, leave ledger, adjustments, encashment. |
| Payroll | Components, contracts, employee contract assignment, salary runs, period commit/undo, employee loans, salary structures, payroll periods, payroll entries, payslips, payroll inputs, Saudi payroll info, WPS batches, EOS provision snapshots, payroll accounting posting, work-entry import. |
| Recruitment | Staffing plans, job requisitions, applicants, interview feedback, offers, offer-to-employee marking. Requires business validation for final approval rules. |
| Performance | Appraisal cycles, goals, competencies, employee goals, competency scores, evaluations, submit/review/approve/cancel flow. Requires business validation for scoring policy. |
| Training | Training programs, events, attendees, attendance, results, certificate links. Requires business validation for training governance. |
| General settings | System settings, home page templates, currencies. |

## Implementation Goals

Establish accurate organization and HR master data.

Configure permission-safe access by role and branch.

Migrate employee records with validated employment, attendance, leave, and payroll attributes.

Enable daily HR operations: employee maintenance, attendance, leave, payroll, recruitment, performance, and training where in scope.

Train each role with the role-based guides in this package.

Complete controlled go-live with sign-offs, support ownership, and post-go-live review.

## Implementation Assumptions

| Assumption | Validation owner |
| --- | --- |
| The company has an approved organization structure before configuration starts. | HR Sponsor |
| Employee source data can be exported to spreadsheet format. | HR Data Owner |
| Payroll rules, components, periods, WPS requirements, and Saudi payroll fields are approved before payroll setup. | Payroll Lead |
| Attendance devices, geolocation rules, shifts, and holiday calendars are agreed before attendance UAT. | Attendance Lead |
| User roles and branch access rules are approved before UAT. | IT Security Lead |
| Arabic and English terminology is reviewed by HR before training. | HR Lead |

## Phase Plan

| Phase | Duration | Main activities | Key deliverables |
| --- | --- | --- | --- |
| 1. Mobilization | Week 1 | Kickoff, governance, stakeholder confirmation, project workspace, document sign-off process. | Project charter, RACI, timeline, issue log. |
| 2. Discovery and Fit | Weeks 1-2 | Confirm HR policies, organization structure, employee lifecycle, attendance, leave, payroll, recruitment, performance, training. | Scope of work, workflow mapping, configuration workbook draft. |
| 3. Data Preparation | Weeks 2-4 | Collect masters, cleanse employee data, map departments/positions, validate payroll and leave balances. | Master data template, employee data template, migration plan. |
| 4. Configuration | Weeks 3-6 | Configure organization, roles, branches, security, HR masters, shifts, leave policies, payroll components and periods. | Configured environment, roles-permissions matrix, configuration sign-off. |
| 5. Migration and Integration Readiness | Weeks 5-7 | Load or enter data, reconcile counts, validate migrated records, prepare attachments and identifiers. | Migration reconciliation, exception log, data sign-off. |
| 6. Testing | Weeks 6-8 | SIT, UAT, role-based workflows, payroll parallel run if payroll is in scope, security testing. | Test plan results, UAT sign-off. |
| 7. Training and Change | Weeks 7-9 | Train administrators, HR, payroll, managers, employees, and specialist roles. | Training attendance, quick references, readiness report. |
| 8. Cutover and Go-Live | Week 10 | Freeze source changes, final migration, final validation, enable users, go-live communications. | Cutover checklist, go-live sign-off. |
| 9. Hypercare | Weeks 10-12 | Daily triage, issue resolution, adoption support, handover to support. | Hypercare log, support handover, post-go-live review. |

## Workstreams

| Workstream | Scope |
| --- | --- |
| Governance | Kickoff, steering committee, status reporting, decisions, risks, issues, change requests. |
| Organization and Security | Company setup, branches, departments, administrations, roles, users, permission assignment, branch access. |
| HR Core | Employees, positions, teams, academic institutions, specializations, lifecycle, documents, skills, certifications. |
| Attendance | Shifts, sessions, check-in rules, holidays, late requests, mid-day permissions, roster, corrections, biometric import. |
| Leave | Leave types, periods, policies, balances, applications, emergency leave, ledger, reports. |
| Payroll | Components, contracts, salary structures, periods, payroll entries, payslips, loans, WPS, Saudi payroll, accounting posting. |
| Talent | Recruitment, performance, and training workflows. |
| Data | Templates, cleansing, migration, reconciliation, attachment tracking. |
| Testing and Training | SIT, UAT, training, role guides, readiness. |
| Go-Live and Support | Cutover, communications, hypercare, support transition. |

## Success Criteria

100% of approved active employees are available in AlafkarHR.

Organization, branch, department, and position structures match approved HR records.

Role-based access is approved and tested for each role.

Attendance, leave, and payroll pilot scenarios are completed successfully.

Critical UAT defects are closed or formally accepted before go-live.

End users complete training or receive approved reference material.

Hypercare triage process is active from the first business day after go-live.

## Business Validation Required

Final payroll calculations, allowances, deductions, EOS, WPS, and accounting posting policy.

Attendance geolocation, biometric import format, late check-in, mid-day permission, correction, and roster approval rules.

Leave accrual, carry-forward, encashment, emergency leave, attachment, and approval rules.

Recruitment approval thresholds, offer approval, and employee creation policy.

Performance rating scales, appraisal cycles, manager review, and approval authority.

Training attendance, result recording, certification, and completion rules.

# Chapter 2: Project Charter

## Project Name

AlafkarHR Company Implementation.

## Project Objective

Implement AlafkarHR as the operational HR system for organization structure, employee records, attendance, leave, payroll, talent processes, role-based access, and HR reporting.

## Business Case

The company requires a centralized HR platform that supports bilingual HR operations, company and branch scoping, role-based permissions, structured employee data, attendance operations, leave control, payroll processing, and management visibility.

## In Scope

Company, branch, administration, department, and business line setup.

User and role setup using AlafkarHR permission groups.

Employee records, employment attributes, positions, teams, specializations, academic institutions.

Employee lifecycle, emergency contacts, document links, skills, and certifications.

Attendance shifts, sessions, holidays, requests, approvals, roster controls, reports, and work entries.

Leave types, periods, policies, applications, balances, ledger, emergency leave, and reports.

Payroll components, contracts, salary structures, periods, entries, payslips, loans, WPS, Saudi payroll information, and payroll accounting posting where approved.

Recruitment, performance, and training configuration after business validation.

Data migration, testing, training, cutover, and hypercare.

## Out of Scope Unless Approved

Application code changes.

Custom integrations not already confirmed.

Custom payroll rule development outside confirmed configuration.

Historical document digitization beyond agreed upload or link scope.

ERPNext or Odoo comparison.

## Key Stakeholders

| Role | Responsibility |
| --- | --- |
| Executive Sponsor | Approves budget, scope, go-live decision. |
| HR Sponsor | Owns HR process decisions and HR readiness. |
| Payroll Lead | Owns payroll setup, payroll testing, and payroll sign-off. |
| IT Lead | Owns users, access, environment readiness, and support transition. |
| Implementation Lead | Coordinates implementation execution and documentation. |
| Department Managers | Validate manager workflows, approvals, and team data. |
| Key Users | Execute UAT and support training. |

## Governance

Weekly project status meeting.

Twice-weekly workstream checkpoints during configuration and testing.

Daily hypercare triage after go-live.

Decision log for policy, data, access, and cutover decisions.

Change request review for any scope not covered by this charter.

## Milestones

| Milestone | Approval owner |
| --- | --- |
| Project charter signed | Executive Sponsor |
| Scope and workflow sign-off | HR Sponsor |
| Data migration sign-off | HR Data Owner |
| Security and role sign-off | IT Lead |
| Payroll parallel run sign-off | Payroll Lead |
| UAT sign-off | Business Leads |
| Go-live approval | Steering Committee |
| Hypercare closure | Executive Sponsor |

## Acceptance Criteria

Required documents in this package are reviewed and approved.

Configuration matches signed business scope.

Migrated data reconciles against approved source files.

UAT pass criteria are met.

Role guides are distributed to target audiences.

Support ownership is agreed before go-live.

# Chapter 3: Scope of Work

## Implementation Scope

AlafkarHR will be implemented for the company as a modular HR operating platform. The scope is based on confirmed repository modules, Blazor pages, service contracts, and permissions.

## Confirmed Functional Scope

| Area | Included functionality |
| --- | --- |
| Security | Login, roles, permissions, user list, user forms, role assignment, security dashboard. |
| Organization | Company list, parent/child company management, branch list/form, administrations, departments, business lines, license categories. |
| Employees | Employee dashboard, employee list/form/view, 360 view, public view, QR view, team setup, positions, academic institutions, specializations. |
| HR enhancements | Command center, lifecycle events, employee documents, emergency contacts, skills, certifications, HR reports. |
| Attendance | Dashboard, sessions, check-in/check-out, breaks, location ping, shifts, assignments, holidays, late check-in requests, mid-day permissions, approvals, reports. |
| Roster | Roster controls, substitute configurations, schedules, assignments, publish/lock/cancel, shift swaps, corrections. |
| Biometric and work entries | Biometric import batches and rows, payroll work-entry generation, edit, approve, lock. |
| Leave | Emergency leave, attachments, review, balances, leave types, periods, policies, assignments, allocations, applications, ledger, adjustments, encashment, reports. |
| Payroll | Components, contracts, employee contracts, salary runs, loan management, structures, periods, entries, payslips, payroll inputs, Saudi payroll, WPS, EOS provision, accounting posting, work-entry import. |
| Recruitment | Staffing plans, requisitions, applicants, interview feedback, offers, offer acceptance/rejection, employee creation marking. |
| Performance | Cycles, goals, competencies, employee goals, competency scores, evaluations, submit/review/approve/cancel. |
| Training | Programs, events, attendees, attendance marking, results, certificate links. |
| Settings | System settings, home page templates, currencies. |

## Technical Scope

Use existing UI pages and API services.

Configure normal permission claims through company roles.

Respect branch access where pages or backend flows use company and branch context.

Use existing bilingual Arabic/English UI behavior.

Use existing data structures and DTO fields.

## Exclusions

| Exclusion | Handling |
| --- | --- |
| Custom code development | Requires separate approved development request. |
| Manual EF migration edits | Not applicable; no application code changes are planned. |
| Unconfirmed external biometric formats | Validate device export format during discovery. |
| Payroll statutory interpretation | Payroll rules must be approved by company payroll/legal owners. |
| Historical archive digitization | Can be planned as separate workstream. |

## Dependencies

Approved organization hierarchy.

Clean employee source data.

Approved payroll and leave rules.

Approved shift, attendance, and holiday policies.

Approved roles and permission assignment.

Availability of key users for UAT and training.

## Validation Notes

Recruitment, performance, and training capabilities are present in service contracts and HR routes; final process design must be validated with HR.

Payroll has extensive confirmed functionality, but calculation rules and statutory interpretations remain business-owned.

Branch visibility and mutation rules must be validated in UAT for each role.

# Chapter 4: Stakeholder Register

| Stakeholder | Interest | Responsibilities | Engagement |
| --- | --- | --- | --- |
| Executive Sponsor | Business outcome and go-live approval. | Resolve escalations, approve scope, approve go-live. | Steering committee and milestone sign-offs. |
| HR Sponsor | HR process readiness. | Approve HR workflows, data standards, training approach. | Weekly workstream review. |
| HR Administrator | Day-to-day HR operations. | Validate employee setup, lifecycle, documents, skills, reports. | Discovery, UAT, training. |
| Payroll Lead | Payroll accuracy and statutory compliance. | Approve payroll configuration, test salary runs, WPS, payslips. | Payroll workshops, parallel run, sign-off. |
| Attendance Lead | Time and attendance operations. | Validate shifts, roster, attendance sessions, requests, corrections, reports. | Attendance workshops and UAT. |
| IT Security Lead | User access and support. | Create users, roles, permissions, branch access, support handover. | Configuration and security testing. |
| Department Managers | Team approval workflows. | Validate team visibility, approvals, reports, manager guide. | UAT and manager training. |
| Employees | Self-service usage. | Use attendance and leave workflows accurately. | Training and go-live communications. |
| Recruiter | Hiring workflow. | Validate staffing plans, requisitions, applicants, interviews, offers. | Recruitment validation workshop. |
| Performance Owner | Appraisal workflow. | Validate cycles, goals, competencies, reviews, approvals. | Performance validation workshop. |
| Training Coordinator | Training operations. | Validate programs, events, attendees, results, certificates. | Training validation workshop. |
| Finance Reviewer | Payroll accounting and cost review. | Validate payroll posting and financial review process. | Payroll/finance testing. |
| Implementation Lead | Delivery ownership. | Manage plan, risks, issues, documents, sign-offs. | Daily delivery coordination. |

## Engagement Principles

Decisions must have a named business owner.

Data owners must approve data before migration.

Key users must test the workflows they will rely on after go-live.

Open issues must be ranked by go-live impact, not only by technical complexity.

# Chapter 5: RACI Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed.

| Activity | Executive Sponsor | HR Sponsor | HR Admin | Payroll Lead | Attendance Lead | IT Lead | Managers | Implementation Lead |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Charter approval | A | C | I | I | I | C | I | R |
| Scope confirmation | A | A | R | R | R | C | C | R |
| Organization setup | I | A | R | C | C | C | C | R |
| Role and permission design | I | C | C | C | C | A/R | C | R |
| Employee data collection | I | A | R | C | C | I | C | R |
| Payroll configuration | I | C | C | A/R | C | I | I | R |
| Attendance configuration | I | C | C | C | A/R | I | C | R |
| Leave configuration | I | A | R | C | C | I | C | R |
| Recruitment validation | I | A | R | I | I | I | C | R |
| Performance validation | I | A | R | I | I | I | C | R |
| Training validation | I | A | R | I | I | I | C | R |
| Data migration | I | A | R | R | R | C | C | R |
| SIT execution | I | C | C | C | C | C | I | A/R |
| UAT execution | I | A | R | R | R | C | R | R |
| Training delivery | I | A | R | R | R | C | C | R |
| Cutover | A | A | R | R | R | A/R | I | R |
| Go-live approval | A | A | C | C | C | C | I | R |
| Hypercare triage | I | A | R | R | R | R | C | R |

# Chapter 6: Data Migration Plan

## Objective

Move approved company HR data into AlafkarHR with traceable cleansing, loading, validation, and sign-off.

## Data Objects

| Data object | Required before | Key fields |
| --- | --- | --- |
| Company | Configuration | Company names, license/status where applicable, business lines. |
| Branches | Employee migration | Branch name/code, main branch, address, active status. |
| Administrations | Employee migration | Administration name, company, branch if applicable. |
| Departments | Employee migration | Department name, administration, branch, attendance location if used. |
| Positions | Employee migration | Position name, grade/category if used, company. |
| Teams | Optional before go-live | Team name, category, members. |
| Employees | UAT | Personal data, identity, contacts, employment, company, branch, administration, department, position, status. |
| Employee documents | UAT or post-go-live wave | Document type, number, issue/expiry dates, attachment/link. |
| Skills and certifications | Optional wave | Skill/certification name, level, issuer, dates. |
| Attendance | Configuration/UAT | Shifts, assignments, holidays, calendars, roster schedules. |
| Leave | Configuration/UAT | Leave types, periods, policies, assignments, balances, open applications. |
| Payroll | Payroll UAT | Components, contracts, structures, assignments, periods, loans, Saudi payroll info, bank/WPS data. |

## Migration Stages

| Stage | Activities | Exit criteria |
| --- | --- | --- |
| Extract | Export source data from legacy HR, spreadsheets, payroll, attendance devices, or manual files. | Source files versioned and owned. |
| Cleanse | Remove duplicates, normalize names, validate IDs, map old departments/positions to target structure. | Exception list reviewed. |
| Map | Map each source field to AlafkarHR target template. | Mapping approved by data owners. |
| Trial load | Load sample or full data into test environment/manual configuration set. | Load errors logged and resolved. |
| Reconcile | Compare counts and key values against source. | Reconciliation signed off. |
| Final load | Apply data freeze and load final approved files. | Final counts match approved totals. |
| Post-load validation | Business users validate records and workflows. | Data sign-off complete. |

## Cleansing Rules

Every active employee must have a valid company, branch, department, and position.

Employee status must be standardized to active, inactive, terminated, or other approved status supported by the system.

Identity numbers, employee numbers, and email addresses must be unique where company policy requires uniqueness.

Arabic and English names should be provided where the business requires bilingual reporting.

Payroll data must be separated from general HR data and approved by payroll owner.

Attachments should be linked using approved filenames and document types.

## Reconciliation

| Check | Tolerance |
| --- | --- |
| Employee count by company | 0 variance unless approved. |
| Employee count by branch | 0 variance unless approved. |
| Employee count by department | 0 variance unless approved. |
| Active/terminated counts | 0 variance unless approved. |
| Leave balance totals | Payroll/HR-approved variance only. |
| Payroll contract assignments | 0 variance for payroll go-live population. |
| Open loans | 0 variance for payroll go-live population. |

## Cutover Data Freeze

Freeze organization, employee, leave, attendance, and payroll changes in legacy sources before final load.

Record emergency changes in a cutover delta log.

Apply deltas after final load and before go-live validation.

## Sign-Off

Data migration is complete only when HR, payroll, attendance, and IT owners sign the migration reconciliation and open exception log.

# Chapter 7: Master Data Collection Template

Use this as a spreadsheet structure. Each table can become a separate worksheet.

## Companies

| Company Code | Company Name EN | Company Name AR | Parent Company | License Category | Business Lines | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Branches

| Branch Code | Branch Name EN | Branch Name AR | Company Code | Is Main Branch | Address | City | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Administrations

| Administration Code | Name EN | Name AR | Company Code | Branch Code | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Departments

| Department Code | Name EN | Name AR | Company Code | Branch Code | Administration Code | Attendance Location | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Positions

| Position Code | Name EN | Name AR | Company Code | Grade | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Teams

| Team Code | Team Name EN | Team Name AR | Company Code | Team Category | Manager Employee No | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Academic Institutions

| Institution Code | Name EN | Name AR | Company Code | Active | Notes |
| --- | --- | --- | --- | --- | --- |

## Specializations

| Specialization Code | Name EN | Name AR | Company Code | Active | Notes |
| --- | --- | --- | --- | --- | --- |

## Shifts

| Shift Code | Name | Company Code | Start Time | End Time | Break Mode | Grace Minutes | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Holidays

| Holiday Name | Company Code | Date From | Date To | Holiday Type | Applies To Branch | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Leave Types

| Leave Type Code | Name EN | Name AR | Company Code | Paid/Unpaid | Requires Attachment | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Leave Periods

| Period Code | Company Code | Year | Start Date | End Date | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Leave Policies

| Policy Code | Name | Company Code | Leave Type | Annual Entitlement | Carry Forward | Encashment Allowed | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Payroll Components

| Component Code | Name | Company Code | Component Type | Calculation Type | Default Amount/Rate | Taxable | Active | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Payroll Periods

| Period Code | Company Code | Month | Year | Start Date | End Date | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Salary Structures

| Structure Code | Name | Company Code | Effective From | Effective To | Active | Components | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

# Chapter 8: Employee Data Collection Template

Use this as a spreadsheet structure. Keep sensitive payroll and identity data access restricted.

## Employee Profile

| Employee No | Name EN | Name AR | Gender | Nationality | Identity Type | Identity No | Date of Birth | Marital Status | Mobile | Email |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Employment Assignment

| Employee No | Company Code | Branch Code | Administration Code | Department Code | Position Code | Manager Employee No | Employment Type | Join Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Employee Lifecycle

| Employee No | Event Type | Effective Date | Requested By | Status | Notes |
| --- | --- | --- | --- | --- | --- |

## Emergency Contacts

| Employee No | Contact Name | Relationship | Mobile | Email | Address | Primary Contact |
| --- | --- | --- | --- | --- | --- | --- |

## Documents

| Employee No | Document Type | Document Number | Issue Date | Expiry Date | Attachment Path/Link | Renewal Required | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Skills

| Employee No | Skill Name | Level | Verified | Verified By | Notes |
| --- | --- | --- | --- | --- | --- |

## Certifications

| Employee No | Certification Name | Issuer | Issue Date | Expiry Date | Attachment Path/Link | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Attendance Setup

| Employee No | Shift Code | Shift Assignment Scope | Effective From | Effective To | Attendance Type | Device/Biometric ID | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Leave Opening Balances

| Employee No | Leave Type Code | Leave Period Code | Opening Balance | Used Balance | Pending Balance | Notes |
| --- | --- | --- | --- | --- | --- | --- |

## Payroll Assignment

| Employee No | Contract Code | Salary Structure Code | Effective From | Effective To | Base Salary | Payment Method | Bank Name | IBAN | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Employee Loans

| Employee No | Loan Type | Principal Amount | Start Date | Installment Amount | Outstanding Amount | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Saudi Payroll Information

| Employee No | GOSI Eligible | GOSI Number | Saudi/NON-Saudi Classification | Housing Basis | Transportation Basis | WPS Required | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

# Chapter 9: Configuration Workbook

## Configuration Principles

Configure company and branch structure before users, employees, attendance, leave, or payroll.

Configure permissions through roles, then assign users to roles.

Keep branch access separate from normal permission claims.

Validate every configuration item with a business owner.

## Organization Configuration

| Item | Required | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| Company record | Yes | HR/IT | Not started |  |
| Main branch | Yes | HR/IT | Not started | Every company must have a main branch. |
| Branches | Yes | HR | Not started |  |
| Administrations | Recommended | HR | Not started |  |
| Departments | Yes | HR | Not started |  |
| Business lines | If licensed/used | HR/IT | Not started |  |
| License categories | If platform-managed | IT | Not started |  |

## Security Configuration

| Item | Required | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| System Administrator role | Yes | IT | Not started | Full setup/security access. |
| HR Administrator role | Yes | HR/IT | Not started | HR master and employee maintenance. |
| Employee role | Yes | HR/IT | Not started | Self-service attendance/leave. |
| Manager role | Yes | HR/IT | Not started | Review/approve team requests. |
| Payroll Officer role | If payroll in scope | Payroll/IT | Not started | Payroll setup and processing. |
| Attendance Officer role | If attendance in scope | Attendance/IT | Not started | Shifts, sessions, reports, approvals. |
| Recruiter role | If recruitment in scope | HR/IT | Not started | Recruitment workflows. |
| Performance Reviewer role | If performance in scope | HR/IT | Not started | Appraisal workflows. |
| Training Coordinator role | If training in scope | HR/IT | Not started | Training workflows. |
| Branch access | If branches in scope | IT | Not started | Assign selected/default branches. |

## HR Core Configuration

| Item | Required | Owner | Status |
| --- | --- | --- | --- |
| Positions | Yes | HR | Not started |
| Teams | Optional | HR | Not started |
| Academic institutions | Optional | HR | Not started |
| Specializations | Optional | HR | Not started |
| Employee document categories | Validate | HR | Not started |
| Lifecycle event types/status rules | Validate | HR | Not started |

## Attendance Configuration

| Item | Required | Owner | Status |
| --- | --- | --- | --- |
| Calendar settings | Yes | Attendance Lead | Not started |
| Shifts | Yes | Attendance Lead | Not started |
| Shift assignments | Yes | Attendance Lead | Not started |
| Holidays | Yes | Attendance Lead | Not started |
| Check-in location rules | Validate | Attendance Lead | Not started |
| Late check-in rules | Validate | Attendance Lead | Not started |
| Mid-day permission rules | Validate | Attendance Lead | Not started |
| Roster schedules | If roster in scope | Attendance Lead | Not started |
| Biometric import format | If biometric in scope | IT/Attendance | Not started |

## Leave Configuration

| Item | Required | Owner | Status |
| --- | --- | --- | --- |
| Leave types | Yes | HR | Not started |
| Leave periods | Yes | HR | Not started |
| Leave policies | Yes | HR | Not started |
| Policy assignments | Yes | HR | Not started |
| Opening balances | Yes | HR | Not started |
| Emergency leave approval rules | Validate | HR | Not started |
| Encashment rules | If in scope | HR/Payroll | Not started |

## Payroll Configuration

| Item | Required | Owner | Status |
| --- | --- | --- | --- |
| Payroll components | Yes | Payroll | Not started |
| Contracts | Yes | Payroll | Not started |
| Employee contract assignments | Yes | Payroll | Not started |
| Salary structures | If structure-based payroll in scope | Payroll | Not started |
| Payroll periods | Yes | Payroll | Not started |
| Payroll entries | Yes | Payroll | Not started |
| Payslip approval and payment rules | Yes | Payroll | Not started |
| Employee loans | If in scope | Payroll | Not started |
| Saudi payroll info | If in scope | Payroll | Not started |
| WPS batches | If in scope | Payroll | Not started |
| Accounting posting | If in scope | Payroll/Finance | Not started |

## Talent Configuration

| Area | Required | Owner | Status |
| --- | --- | --- | --- |
| Recruitment staffing plans | If recruitment in scope | HR | Requires validation |
| Job requisition workflow | If recruitment in scope | HR | Requires validation |
| Appraisal cycles | If performance in scope | HR | Requires validation |
| Goals and competencies | If performance in scope | HR | Requires validation |
| Training programs | If training in scope | HR | Requires validation |
| Training event workflow | If training in scope | HR | Requires validation |

# Chapter 10: Roles and Permissions Matrix

## Permission Model

AlafkarHR uses permission strings grouped by module and entity. Normal company-wide authorization is based on Permission claims. Branch access permissions such as Organization.BranchAccess.ViewAll and branch assignments are additional visibility controls and do not replace normal permissions.

## Recommended Roles

| Role | Purpose | Main permission groups |
| --- | --- | --- |
| System Administrator | Full setup, security, organization, and support administration. | Authentication.Users, Authentication.Roles, Organization.Company, Organization.Branch, Organization.Administration, Organization.Department, GeneralSettings.SystemSettings. |
| HR Administrator | Own employee master data and HR operations. | Employees.Employee, Employees.Team, Employees.Position, Employees.AcademicInistitution, Employees.Specialization, Employees.Lifecycle, Employees.Document, Employees.Skill, Leave.Policy, Leave.Application, Leave.Ledger. |
| Employee | Use self-service attendance and leave. | Attendance.Attendance request/view actions, Leave.Leave.RequestEmergencyLeave, Leave.Application request/cancel actions, limited employee view where allowed. |
| Manager/Supervisor | Review team attendance/leave and inspect team HR data. | Attendance.Attendance.ReviewRequests, Attendance.Attendance.ApproveMidDayPermission, Attendance.Roster.ApproveSwap, Leave.Leave.ApproveEmergencyLeave, Leave.Application.Approve, Employees.Employee.View. |
| Payroll Officer | Configure and run payroll. | Payroll.Contract, Payroll.Loan, Payroll.SalaryRun, Payroll.Structure, Payroll.Payslip, Payroll.WorkEntry. |
| Attendance Officer | Manage attendance configuration and exceptions. | Attendance.Attendance, Attendance.Roster, Attendance.WorkEntry. |
| Recruiter | Manage recruitment process. | HR.Recruitment. |
| Performance Reviewer | Manage performance cycles and reviews. | HR.Performance. |
| Training Coordinator | Manage training programs/events/attendees. | HR.Training. |
| Finance Reviewer | Review payroll output and accounting posting. | Payroll.Payslip view/approve as approved, Accounting.Document/JournalEntry where finance module is in scope. |
| Executive/Management | View dashboards and reports. | View/report permissions only for HR, attendance, leave, payroll, and organization as approved. |

## Permission Assignment Matrix

| Permission group | System Admin | HR Admin | Employee | Manager | Payroll | Attendance | Recruiter | Performance | Training | Executive |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Authentication.Users | CRUD | - | - | - | - | - | - | - | - | - |
| Authentication.Roles | CRUD | - | - | - | - | - | - | - | - | - |
| Organization.Company | View/Edit | View | - | View | View | View | - | - | - | View |
| Organization.Branch | CRUD + AssignUsers | View | - | View | View | View | - | - | - | View |
| Organization.Administration | CRUD | View | - | View | View | View | - | - | - | View |
| Organization.Department | CRUD | CRUD | - | View | View | View | - | - | - | View |
| Employees.Employee | CRUD | CRUD | Own view if configured | View team | View payroll population | View | Candidate conversion support | View | View | View/report |
| Employees.Lifecycle | CRUD/approve | CRUD/approve | - | View/approve if policy allows | View | - | - | - | - | Report |
| Employees.Document | CRUD/renew | CRUD/renew | Own documents if configured | View team if approved | View payroll documents if approved | - | - | - | - | Report |
| Employees.Skill | CRUD/verify | CRUD/verify | Own skills if configured | View team | - | - | - | Performance input | Training input | Report |
| Attendance.Attendance | Full | View/report | My attendance/request | Review/approve | Work-entry dependency | Full | - | - | - | Reports |
| Attendance.Roster | Full | View | View own | Approve swap if approved | Work-entry dependency | Full | - | - | - | Reports |
| Attendance.WorkEntry | Full | View | - | Review if approved | Generate/edit/approve | Generate/edit/approve | - | - | - | Reports |
| Leave.Leave | Full | Manage | Request | Approve | View payroll impact | - | - | - | - | Reports |
| Leave.Policy | Full | CRUD/assign | - | View | View | - | - | - | - | View |
| Leave.Application | Full | CRUD/review | Request/cancel | Approve | View payroll impact | - | - | - | - | Reports |
| Leave.Ledger | Full | View/adjust | Own balance if configured | View team | View/encash if approved | - | - | - | - | Reports |
| Payroll.Contract | Full | View | - | - | CRUD | - | - | - | - | Reports |
| Payroll.Loan | Full | View | - | - | CRUD/approve/cancel | - | - | - | - | Reports |
| Payroll.SalaryRun | Full | View | - | - | Create/edit/approve | Work-entry dependency | - | - | - | Reports |
| Payroll.Structure | Full | View | - | - | CRUD/activate/assign | - | - | - | - | Reports |
| Payroll.Payslip | Full | View | Own payslip if configured | - | Generate/approve/pay/cancel | - | - | - | - | Reports |
| HR.Recruitment | Full | View | - | Interview input if approved | - | - | CRUD/approve/hire | - | - | Reports |
| HR.Performance | Full | View | Own feedback if configured | Review | - | - | - | CRUD/review/approve | - | Reports |
| HR.Training | Full | View | Attend/view if configured | Nominate/review if approved | - | - | - | - | CRUD/complete | Reports |

CRUD means select, view, create, edit, and delete where the permission group supports those actions.

## Access Approval Checklist

[ ] Role names approved by HR and IT.

[ ] Permission groups mapped to each role.

[ ] Branch access reviewed for each user.

[ ] Default branch assignment confirmed where branch assignment is used.

[ ] No role grants payroll edit rights to non-payroll users.

[ ] No role grants security administration to business-only users.

[ ] UAT includes negative tests for unauthorized pages/actions.

# Chapter 11: Workflow Mapping

## Organization Setup

Create or confirm company.

Ensure main branch exists.

Create branches.

Create administrations and departments.

Create positions and optional teams.

Validate branch and department visibility with security roles.

## User and Role Setup

Define roles using the roles-permissions matrix.

Create roles in /Auth/Role/List.

Create or confirm users in /Auth/User/List.

Assign roles in /Auth/User/AssignRole.

Assign branch access where the user should be limited to selected branches.

Test menu visibility and page access.

## Employee Creation

Confirm required organization masters exist.

Open /Employee/Employee/List.

Create employee from /Employee/Employee/Form/{Id?}.

Assign company, branch, administration, department, and position.

Add emergency contacts, documents, skills, certifications, and lifecycle events where required.

Review employee view or 360 view.

## Employee Lifecycle

Open /HR/EmployeeLifecycle.

Select employee.

Add lifecycle event.

Submit or transition event based on approved workflow.

Manager or HR approver reviews where approval is required.

Complete the lifecycle event and verify employee record impact.

## Attendance Daily Work

Employee opens /Attendance/MyAttendance.

Employee checks preview if location rules are used.

Employee starts session, starts/ends break if applicable, and ends session.

Attendance officer reviews sessions in /Attendance/Sessions.

Exceptions are handled through late check-in requests, mid-day permission requests, or attendance corrections.

Attendance reports are reviewed in /Attendance/Reports.

## Attendance Setup and Roster

Configure calendar settings and holidays.

Configure shifts in /Attendance/Shifts.

Assign shifts in /Attendance/ShiftAssignments.

Configure roster schedules in /HR/AttendanceRoster where roster is in scope.

Publish or lock schedules after validation.

Review shift swaps and corrections where applicable.

## Leave Application

HR configures leave types, periods, policies, assignments, and balances.

Employee opens /LeavesManagement/MyLeaveApplications.

Employee creates leave application and uploads attachment if required.

Employee submits request.

Manager/HR reviews the application.

Approved application updates leave workflow and reports.

HR monitors ledger and balances through /HR/LeaveLedger and /LeavesManagement/Balances.

## Emergency Leave

Employee or HR creates emergency leave request.

Attachment is uploaded where policy requires it.

Approver opens /LeavesManagement/ApproveEmergencyLeaves.

Approver approves or rejects request with comments.

HR reviews report impact.

## Payroll Run

Configure components and contracts.

Assign contracts and salary structures to employees.

Configure payroll period.

Import or generate attendance work entries if attendance is used.

Create payroll entry or salary run.

Generate/recalculate payslips.

Review payroll inputs, loans, Saudi payroll data, and WPS batches.

Approve payslips or salary runs.

Mark payslips paid where applicable.

Post payroll accounting if finance integration is in scope.

## Recruitment

Create staffing plan.

Create job requisition.

Open requisition.

Add applicants.

Record interview feedback.

Create job offer.

Accept/reject offer.

Mark employee created when candidate is hired.

Requires validation: approval thresholds, offer approvals, and employee creation ownership.

## Performance

Create appraisal cycle.

Create goals and competencies.

Start cycle.

Create employee evaluations.

Employee submits feedback if enabled by policy.

Manager reviews.

HR or approver approves.

Close cycle.

Requires validation: rating scale, weighting, calibration, and approval authority.

## Training

Create training program.

Create training event.

Open/start event.

Add attendees.

Mark attendance.

Record results.

Link certificates.

Complete event.

Requires validation: nomination rules, training budget, certificate policy, and completion criteria.

# Chapter 12: Test Plan

## Test Objectives

Prove that configured AlafkarHR workflows support the company operating model.

Validate migrated data accuracy.

Confirm permission and branch access security.

Confirm payroll, attendance, and leave outputs before go-live.

## Test Types

| Test type | Purpose | Owner |
| --- | --- | --- |
| Configuration smoke test | Confirm configured pages open and save records. | Implementation Lead |
| System integration test | Test cross-module flows such as employee to attendance, leave, payroll. | Implementation Lead |
| Data migration test | Reconcile loaded data. | Data Owner |
| Security test | Confirm role and branch restrictions. | IT Lead |
| UAT | Business users validate real work scenarios. | Business Leads |
| Payroll parallel test | Compare AlafkarHR payroll outputs to approved payroll results. | Payroll Lead |
| Regression test | Retest critical workflows after fixes. | Implementation Lead |

## Entry Criteria

Scope signed.

Configuration workbook populated.

Test users and roles created.

Test data loaded.

UAT scripts approved.

## Exit Criteria

All critical defects closed.

High defects closed or accepted with workaround.

UAT sign-off completed.

Payroll parallel run signed if payroll is in scope.

Security test passed.

## Defect Severity

| Severity | Meaning | Go-live impact |
| --- | --- | --- |
| Critical | Blocks core HR/payroll/attendance/leave operation or exposes unauthorized data. | Must fix before go-live. |
| High | Major workflow failure with limited workaround. | Fix or formal approval required. |
| Medium | Usability or data issue with workaround. | Can defer with owner approval. |
| Low | Cosmetic or minor improvement. | Can defer. |

## Minimum Test Coverage

Organization setup and branch visibility.

Role creation and user role assignment.

Employee create, edit, view, transfer, position change, termination.

Employee documents, lifecycle, skills, certifications.

Attendance shifts, sessions, late request, mid-day permission, holidays, reports.

Leave policies, balances, applications, emergency leave, approvals, ledger.

Payroll components, contracts, salary structures, periods, runs, payslips, loans, WPS, Saudi payroll.

Recruitment, performance, and training where activated.

Reports and dashboards available to intended roles only.

# Chapter 13: UAT Test Scripts

## Script Format

| Field | Description |
| --- | --- |
| Scenario ID | Unique scenario reference. |
| Role | User role executing the scenario. |
| Preconditions | Required data, role, and configuration. |
| Steps | Actions the tester performs. |
| Expected Result | System result required for pass. |
| Status | Pass, fail, blocked, not run. |

## Core Scripts

| ID | Role | Scenario | Steps | Expected result |
| --- | --- | --- | --- | --- |
| UAT-001 | System Administrator | Create role | Open roles, create role, assign permissions, save. | Role is created and visible for assignment. |
| UAT-002 | System Administrator | Assign user role | Open user role assignment, choose user, assign role, save. | User receives expected menu/page access. |
| UAT-003 | HR Administrator | Create employee | Open employee list, create employee, assign branch/department/position, save. | Employee appears in list and view page. |
| UAT-004 | HR Administrator | Update employee assignment | Change department or position. | Employee record reflects new assignment. |
| UAT-005 | HR Administrator | Add employee document | Open HR employee documents, add document data/link. | Document appears for employee. |
| UAT-006 | HR Administrator | Add lifecycle event | Add lifecycle event and transition it. | Lifecycle status changes as expected. |
| UAT-007 | Employee | Check attendance | Open My Attendance, start session, start/end break, end session. | Attendance session is recorded. |
| UAT-008 | Attendance Officer | Review attendance session | Open sessions and filter employee/date. | Session appears with correct status. |
| UAT-009 | Employee | Submit mid-day permission | Create permission request. | Request is pending review. |
| UAT-010 | Manager | Approve mid-day permission | Open approval page, approve request. | Request status changes to approved. |
| UAT-011 | Attendance Officer | Configure shift | Create shift and assign employee. | Shift and assignment are available. |
| UAT-012 | Employee | Submit leave application | Open my leave applications, create and submit. | Application is submitted/pending. |
| UAT-013 | Manager | Approve leave application | Review submitted leave. | Application is approved and visible in reports. |
| UAT-014 | HR Administrator | Maintain leave balance | Open leave balances, adjust balance. | Balance is saved and reflected in reports. |
| UAT-015 | Payroll Officer | Create payroll component | Create earning/deduction component. | Component is available for structures/contracts. |
| UAT-016 | Payroll Officer | Assign contract | Assign contract to employee. | Employee contract appears in payroll list. |
| UAT-017 | Payroll Officer | Run payroll | Create/generate payroll entry or salary run. | Payroll output generated for selected period. |
| UAT-018 | Payroll Officer | Approve payslip | Review and approve payslip. | Payslip status changes to approved. |
| UAT-019 | Payroll Officer | Employee loan | Create, approve, and cancel loan test cases. | Loan status follows expected actions. |
| UAT-020 | Recruiter | Recruitment flow | Create requisition, add applicant, record interview, create offer. | Applicant and offer statuses update. |
| UAT-021 | Performance Reviewer | Appraisal flow | Create cycle, goals, evaluation, submit/review/approve. | Evaluation reaches approved status. |
| UAT-022 | Training Coordinator | Training event | Create program/event, add attendee, mark attendance/result, complete. | Event and attendee statuses update. |
| UAT-023 | Executive | Dashboard/report access | Open HR, attendance, leave, and payroll reports allowed for role. | Reports open without edit access. |
| UAT-024 | Unauthorized user | Negative security test | Attempt restricted payroll/security page. | Access is denied or menu is hidden. |

## Sign-Off

UAT is accepted when all critical and high scenarios pass or have signed business acceptance with workaround.

# Chapter 14: Training Plan

## Training Objectives

Prepare each role to perform daily AlafkarHR work without relying on the implementation team.

Explain data ownership, approval responsibilities, and escalation paths.

Make role-based user guides the primary reference after go-live.

## Training Tracks

| Track | Audience | Topics | Duration |
| --- | --- | --- | --- |
| System Administration | IT administrators | Login, users, roles, permissions, branch access, general settings, support. | 1 day |
| HR Administration | HR team | Organization masters, employees, lifecycle, documents, skills, leave setup, reports. | 2 days |
| Attendance | Attendance officers and managers | Shifts, sessions, holidays, requests, approvals, reports, roster. | 1 day |
| Payroll | Payroll team and finance reviewers | Components, contracts, structures, periods, loans, payroll entries, payslips, WPS, Saudi payroll, accounting posting. | 2 days |
| Employee Self-Service | Employees | My attendance, leave applications, emergency leave, basic profile/reference behavior. | 1-2 hours |
| Manager Self-Service | Managers/supervisors | Team review, approvals, attendance/leave exceptions, reports. | Half day |
| Talent | Recruitment, performance, training owners | Requisitions/applicants/offers, appraisals, training events. | 1 day |
| Executive | Leadership | Dashboards, reports, interpretation, escalation. | 1 hour |

## Training Materials

Role guides in this documentation package.

UAT scripts converted to practice exercises.

Company-specific policy notes.

Go-live support contacts.

Known limitations and business validation decisions.

## Training Readiness Checklist

[ ] Training environment or configured production preview is available.

[ ] Demo users exist for each role.

[ ] Sample employee and payroll data are prepared.

[ ] User guides are reviewed by business owners.

[ ] Attendance tracking sheet is ready.

[ ] Feedback form is ready.

## Training Completion Criteria

Administrators complete role and data setup exercises.

HR administrators complete employee and leave exercises.

Payroll officers complete at least one payroll run exercise.

Managers complete approval exercises.

Employees receive self-service training or communications.

# Chapter 15: Communication and Change Management Plan

## Change Objectives

Help users understand why AlafkarHR is being introduced.

Reduce go-live confusion through early communication and role-based training.

Move HR, attendance, leave, and payroll processes to the agreed system of record.

## Audience Messages

| Audience | Key message |
| --- | --- |
| Leadership | AlafkarHR centralizes HR operations, improves control, and enables reporting. |
| HR Team | HR will own employee data, leave setup, lifecycle records, and HR support. |
| Payroll Team | Payroll workflows will depend on approved employee, attendance, leave, and payroll setup. |
| Managers | Managers will review team requests and use system reports for daily decisions. |
| Employees | Employees will use AlafkarHR for attendance and leave self-service where assigned. |
| IT Support | IT will own user access, roles, branch access, and first-line access support. |

## Communication Timeline

| Timing | Communication | Sender |
| --- | --- | --- |
| Project kickoff | Project announcement and objectives. | Executive Sponsor |
| Discovery complete | Confirmed scope and implementation timeline. | HR Sponsor |
| Before UAT | UAT schedule and tester responsibilities. | Implementation Lead |
| Before training | Training schedule and role guide links. | HR Sponsor |
| One week before go-live | Go-live date, support contacts, key changes. | Executive Sponsor |
| Go-live day | System is live, support channel active. | HR/IT |
| Hypercare | Daily known issues and resolutions where needed. | Support Lead |

## Change Risks

| Risk | Mitigation |
| --- | --- |
| Users keep using legacy spreadsheets. | Confirm cutover date and stop legacy process except approved fallback. |
| Managers do not approve requests on time. | Train managers and send go-live reminders. |
| Payroll distrusts output. | Run parallel payroll and reconcile before go-live. |
| Employees do not understand self-service. | Provide short training and simple guide. |
| Access too broad or too narrow. | Run security UAT and branch access checks. |

## Adoption Measures

Training attendance by role.

Number of unresolved access issues after go-live.

Percentage of leave/attendance requests submitted in system.

Payroll run completion and reconciliation results.

Support ticket trend during hypercare.

# Chapter 16: Go-Live Checklist

## Governance

[ ] Steering committee approves go-live.

[ ] Open critical/high issues reviewed.

[ ] Business owners sign UAT.

[ ] Support and escalation contacts confirmed.

## Configuration

[ ] Company and main branch configured.

[ ] Branches, administrations, departments, positions configured.

[ ] Roles and permissions configured.

[ ] Branch access assigned where required.

[ ] General settings reviewed.

[ ] Currencies configured if payroll/accounting uses them.

## Data

[ ] Employee data loaded or manually entered.

[ ] Employee counts reconciled by company, branch, department, status.

[ ] Leave balances validated.

[ ] Payroll contracts, structures, loans, and Saudi payroll info validated.

[ ] Attendance shifts and assignments validated.

[ ] Attachments/document links validated where in scope.

## Testing

[ ] SIT complete.

[ ] UAT complete.

[ ] Security negative tests complete.

[ ] Payroll parallel run complete if payroll is in scope.

[ ] Reports validated by owners.

## Training

[ ] System administrators trained.

[ ] HR administrators trained.

[ ] Payroll officers trained.

[ ] Attendance officers trained.

[ ] Managers trained.

[ ] Employees notified and trained.

[ ] Role guides distributed.

## Cutover

[ ] Legacy data freeze announced.

[ ] Final data load complete.

[ ] Delta changes applied.

[ ] Test users replaced or disabled where needed.

[ ] Production users enabled.

[ ] Go-live communication sent.

## Hypercare

[ ] Hypercare channel open.

[ ] Daily triage schedule agreed.

[ ] Issue register ready.

[ ] Support handover date agreed.

# Chapter 17: Cutover Plan

## Cutover Objective

Move the company from legacy HR operations to AlafkarHR with controlled data freeze, final validation, user enablement, and rollback decision points.

## Cutover Roles

| Role | Responsibility |
| --- | --- |
| Cutover Manager | Owns cutover plan, timing, decisions, and status. |
| HR Data Owner | Approves final employee and leave data. |
| Payroll Owner | Approves payroll data and readiness. |
| IT Lead | Enables users, validates roles, resolves access issues. |
| Implementation Lead | Executes configuration and validation support. |
| Business Testers | Validate final production records. |

## Sequence

| Step | Activity | Owner | Status |
| --- | --- | --- | --- |
| 1 | Announce freeze window. | HR Sponsor | Not started |
| 2 | Export final source data. | Data Owners | Not started |
| 3 | Apply final data cleansing and delta log. | Data Owners | Not started |
| 4 | Load or enter final organization and employee data. | Implementation/HR | Not started |
| 5 | Validate employee counts and key attributes. | HR | Not started |
| 6 | Validate leave balances and open requests. | HR | Not started |
| 7 | Validate attendance shifts and assignments. | Attendance Lead | Not started |
| 8 | Validate payroll contracts, structures, loans, periods. | Payroll Lead | Not started |
| 9 | Validate roles, users, branch access. | IT Lead | Not started |
| 10 | Send go-live communication. | HR/IT | Not started |
| 11 | Enable production usage. | IT Lead | Not started |
| 12 | Start hypercare. | Support Lead | Not started |

## Rollback Decision Points

Rollback or go-live delay must be considered if:

Active employee data has material unreconciled variance.

Payroll go-live population is incomplete.

Critical permissions expose confidential employee or payroll data.

Attendance or leave workflows cannot be completed by target users.

Production access is unavailable for critical roles.

## Post-Go-Live Day 1 Checks

Users can log in.

Menus reflect assigned roles.

HR can find employee records.

Employees can access assigned self-service pages.

Managers can access approval pages.

Payroll can view required payroll setup.

Support channel is receiving and triaging issues.

# Chapter 18: Support and Hypercare Plan

## Hypercare Duration

Recommended duration: two weeks after go-live, extendable if payroll or attendance issues remain open.

## Support Channels

| Channel | Purpose | Owner |
| --- | --- | --- |
| Hypercare chat/channel | Fast triage for go-live issues. | Support Lead |
| Issue register | Formal tracking, severity, owner, status. | Implementation Lead |
| HR helpdesk | Employee process questions. | HR Admin |
| IT helpdesk | Login, role, access, browser, environment issues. | IT Lead |
| Payroll support | Payroll run and payslip issues. | Payroll Lead |

## Triage Categories

| Category | Examples | First owner |
| --- | --- | --- |
| Access | Login, missing menu, wrong role, branch visibility. | IT Lead |
| Employee data | Wrong department, missing document, incorrect status. | HR Admin |
| Attendance | Check-in issue, shift mismatch, exception approval. | Attendance Officer |
| Leave | Balance issue, application status, attachment problem. | HR Admin |
| Payroll | Contract, component, run, payslip, loan, WPS issue. | Payroll Lead |
| Training/process | User does not know how to complete task. | HR/Implementation |

## SLA During Hypercare

| Severity | Response target | Resolution target |
| --- | --- | --- |
| Critical | 1 business hour | Same day or workaround |
| High | 4 business hours | 2 business days |
| Medium | 1 business day | 5 business days |
| Low | 2 business days | Planned backlog |

## Daily Hypercare Agenda

Review new issues.

Confirm severity and owner.

Review blockers for HR, attendance, leave, and payroll.

Confirm user communication needs.

Close resolved issues with business confirmation.

## Handover to Steady-State Support

Hypercare can close when:

Critical/high issues are closed or accepted.

Support team can handle common access and process questions.

Updated role guides or FAQs are published.

Open backlog has owners and target dates.

# Chapter 19: Risk and Issue Register

## Risk Register

| ID | Risk | Impact | Probability | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Employee source data is incomplete or inconsistent. | High | Medium | Start data profiling early and use templates. | HR Data Owner | Open |
| R-002 | Payroll rules are not approved before configuration. | High | Medium | Schedule payroll policy workshop and require sign-off. | Payroll Lead | Open |
| R-003 | Roles grant excessive access to payroll or employee data. | High | Medium | Use permission matrix and negative security UAT. | IT Lead | Open |
| R-004 | Branch access is misunderstood as authorization. | High | Medium | Train IT and test normal permissions plus branch visibility. | IT Lead | Open |
| R-005 | Managers are unavailable for UAT. | Medium | Medium | Nominate backup testers and publish schedule early. | HR Sponsor | Open |
| R-006 | Attendance device import format is not confirmed. | Medium | Medium | Validate biometric import file format during discovery. | Attendance Lead | Open |
| R-007 | Leave balances are disputed at go-live. | High | Medium | Reconcile balances and sign off before cutover. | HR Lead | Open |
| R-008 | Users continue legacy process after go-live. | Medium | Medium | Clear cutover communication and manager enforcement. | Executive Sponsor | Open |

## Issue Register

| ID | Issue | Severity | Owner | Target Date | Status | Resolution |
| --- | --- | --- | --- | --- | --- | --- |
| I-001 | To be populated during implementation. | TBD | TBD | TBD | Open |  |

## Decision Log

| ID | Decision | Owner | Date | Impact |
| --- | --- | --- | --- | --- |
| D-001 | To be populated during implementation. | TBD | TBD |  |

# Chapter 20: Sign-Off Templates

## Phase Sign-Off

| Field | Value |
| --- | --- |
| Phase |  |
| Deliverables reviewed |  |
| Open issues |  |
| Approved to proceed | Yes / No |
| Approver name |  |
| Role |  |
| Date |  |
| Comments |  |

## Data Migration Sign-Off

| Check | Result | Comments |
| --- | --- | --- |
| Employee counts reconciled | Pass / Fail |  |
| Branch/department assignments reconciled | Pass / Fail |  |
| Leave balances reconciled | Pass / Fail |  |
| Payroll data reconciled | Pass / Fail |  |
| Exceptions approved | Pass / Fail |  |

Approver:

Date:

## UAT Sign-Off

| Field | Value |
| --- | --- |
| UAT cycle |  |
| Scripts executed |  |
| Passed |  |
| Failed |  |
| Blocked |  |
| Critical issues open |  |
| High issues open |  |
| Approved for go-live | Yes / No |

Approver:

Date:

## Training Sign-Off

| Audience | Planned attendees | Completed | Exceptions |
| --- | --- | --- | --- |
| System Administrators |  |  |  |
| HR Administrators |  |  |  |
| Payroll Officers |  |  |  |
| Attendance Officers |  |  |  |
| Managers |  |  |  |
| Employees |  |  |  |

Approver:

Date:

## Go-Live Sign-Off

| Readiness Area | Status | Owner Comments |
| --- | --- | --- |
| Configuration | Ready / Not ready |  |
| Data | Ready / Not ready |  |
| Security | Ready / Not ready |  |
| Testing | Ready / Not ready |  |
| Training | Ready / Not ready |  |
| Support | Ready / Not ready |  |

Go-live decision: Approved / Delayed

Executive Sponsor:

Date:

# Chapter 21: Post-Go-Live Review

## Review Timing

Conduct the review after the first payroll cycle or two weeks after go-live, whichever is later.

## Review Participants

Executive Sponsor

HR Sponsor

HR Administrator

Payroll Lead

Attendance Lead

IT Lead

Implementation Lead

Manager representative

Employee representative if appropriate

## Review Questions

| Area | Questions |
| --- | --- |
| Adoption | Are users completing attendance, leave, HR, and payroll tasks in AlafkarHR? |
| Data | Are employee, leave, payroll, and organization records accurate? |
| Security | Are roles and branch access working as intended? |
| Payroll | Did the payroll cycle complete accurately and on time? |
| Attendance | Are sessions, exceptions, and reports reliable? |
| Leave | Are balances, applications, and approvals reliable? |
| Support | Are issues resolved within target times? |
| Training | Which roles need extra support? |

## Metrics

| Metric | Target | Actual |
| --- | --- | --- |
| Critical issues open | 0 |  |
| High issues open | 0 or accepted |  |
| Payroll reconciliation variance | Approved tolerance |  |
| Leave balance disputes | Downward trend |  |
| Access issues | Downward trend |  |
| Training completion | 95%+ for target users |  |

## Improvement Backlog

| ID | Improvement | Priority | Owner | Target Date |
| --- | --- | --- | --- | --- |
| B-001 |  |  |  |  |

## Closure Decision

Hypercare closure approved: Yes / No

Support handover complete: Yes / No

Approver:

Date:

# Chapter 22: User Guide: System Administrator

## Role Purpose

The System Administrator manages organization setup, users, roles, permissions, branch access, and general system settings.

## Main Pages

Security dashboard: /Auth/Dashboard

Roles: /Auth/Role/List, /Auth/Role/Form

Users: /Auth/User/List, /Auth/User/Form

Assign user roles: /Auth/User/AssignRole

Organization: /Organization/Dashboard, /Organization/Company/List, /Organization/Branch/List, /Organization/Administration/List, /Organization/Department/List

Settings: /GeneralSettings/SystemSettings, /GeneralSettings/HomePageTemplates, /GeneralSettings/Currencies

## Required Permissions

Authentication.Users.*

Authentication.Roles.*

Organization.Company.*

Organization.Branch.*

Organization.Branch.AssignUsers

Organization.BranchAccess.ViewAll where company policy allows all-branch visibility

Organization.Administration.*

Organization.Department.*

GeneralSettings.SystemSettings.*

## Daily Tasks

### Create or Update a Role

Open /Auth/Role/List.

Select create or edit.

Enter role name and description.

Select permission groups needed by the role.

Save.

Test with a user assigned to that role.

### Assign Roles to a User

Open /Auth/User/AssignRole.

Select the user.

Select the approved role or roles.

Save assignment.

Ask the user to sign out and sign in if access does not refresh.

### Validate Branch Access

Confirm the user has the correct normal permissions.

Assign branch access where the user should be limited by branch.

Confirm default branch is included in selected branches.

Test filtered pages such as employee, attendance, payroll, and reports.

### Maintain Organization Setup

Confirm company and main branch exist.

Maintain branches, administrations, departments, and business lines.

Avoid deleting active structures that are referenced by employees or payroll.

## Common Mistakes

| Mistake | Avoidance |
| --- | --- |
| Granting branch view-all without business approval. | Use least privilege and document approval. |
| Assuming branch access replaces permission claims. | Always assign both normal permissions and branch access. |
| Giving payroll edit access to HR users by default. | Keep payroll permissions restricted to payroll roles. |
| Editing roles during payroll processing without notice. | Use change windows and communicate. |

## Troubleshooting

| Symptom | Check |
| --- | --- |
| User cannot see a menu item. | Role permission group, branch access, sign-in refresh. |
| User sees too much data. | Branch access, view-all permissions, role overlap. |
| User can view but not edit. | Edit/create/delete action permissions. |
| Role changes do not apply. | User token/session refresh may be required. |

## Escalation

Escalate unresolved access defects to IT Lead and Implementation Lead. Escalate permission policy decisions to HR Sponsor and Executive Sponsor.

# Chapter 23: User Guide: HR Administrator

## Role Purpose

The HR Administrator owns employee master data, HR structure, employee lifecycle records, documents, skills, leave setup, leave balances, and HR reporting.

## Main Pages

Employee dashboard: /Employee/Dashboard

Employee list/form/view: /Employee/Employee/List, /Employee/Employee/Form/{Id?}, /Employee/Employee/view/{Id}, /Employee/Employee/360/{Id}

HR command center: /HR/CommandCenter

Lifecycle: /HR/EmployeeLifecycle

Documents: /HR/EmployeeDocuments

Skills: /HR/EmployeeSkills

Emergency contacts: /HR/EmployeeEmergencyContacts

Positions: /Employee/Position/List

Teams: /Employee/Teams

Academic institutions: /Employee/AcademicInistitution/List

Specializations: /Employee/Specialization/List

Leave setup and operations: /HR/LeavePolicies, /HR/LeaveApplications, /HR/LeaveLedger, /LeavesManagement/Balances, /LeavesManagement/Reports

## Required Permissions

Employees.Employee.*

Employees.Team.*

Employees.Position.*

Employees.AcademicInistitution.*

Employees.Specialization.*

Employees.Lifecycle.*

Employees.Document.*

Employees.Skill.*

Leave.Policy.*

Leave.Application.*

Leave.Ledger.*

Leave.Leave.* as approved

## Employee Record Workflow

Confirm branch, administration, department, and position exist.

Open /Employee/Employee/List.

Create or edit employee.

Fill personal, identity, contact, and employment assignment fields.

Save and verify the employee in list and view pages.

Add emergency contacts, documents, skills, certifications, and lifecycle events if required.

## Employee Change Workflow

| Change | Where to perform | Validation |
| --- | --- | --- |
| Position change | Employee form or employee action where available. | New position is active and approved. |
| Department transfer | Employee action/service-backed workflow. | New department belongs to correct company/branch. |
| Termination | Employee termination workflow. | Effective date, reason, payroll impact approved. |
| Document renewal | /HR/EmployeeDocuments | Expiry and attachment/link updated. |
| Skill verification | /HR/EmployeeSkills | Verification authority approved. |

## Leave Administration

Maintain leave types, periods, and policies in /HR/LeavePolicies.

Assign leave policies to employees or groups as approved.

Generate or enter allocations.

Maintain balances in /LeavesManagement/Balances.

Review applications in /HR/LeaveApplications.

Use /HR/LeaveLedger for adjustments and encashment when approved.

Use /LeavesManagement/Reports for monitoring.

## Data Entry Rules

Use approved employee numbers and identity values.

Do not create duplicate employees.

Keep company, branch, administration, department, and position aligned.

Attachments or document links must follow company naming rules.

Do not adjust leave balances without approval and notes.

## Common Mistakes

| Mistake | Avoidance |
| --- | --- |
| Creating employee before department or position exists. | Complete organization setup first. |
| Updating payroll-sensitive fields without payroll notice. | Notify payroll before changes affecting salary or employment status. |
| Leaving documents without expiry dates. | Capture issue/expiry dates where applicable. |
| Manual leave balance changes without approval. | Use sign-off and keep notes. |

## Troubleshooting

| Symptom | Check |
| --- | --- |
| Employee missing from list. | Company/branch filters, status, search text, permission. |
| Cannot edit employee. | Employees.Employee.Edit permission. |
| Cannot see leave setup. | Leave policy/application/ledger permissions. |
| Manager cannot see employee. | Manager role, branch access, team/department scope. |

## Escalation

Escalate access issues to IT. Escalate policy conflicts to HR Sponsor. Escalate payroll-sensitive corrections to Payroll Lead.

# Chapter 24: User Guide: Employee

## Role Purpose

Employees use AlafkarHR for assigned self-service activities such as attendance, leave applications, emergency leave, and viewing permitted personal information.

## Main Pages

My attendance: /Attendance/MyAttendance

My leave applications: /LeavesManagement/MyLeaveApplications

Emergency leave requests: /LeavesManagement/EmergencyLeaves

Employee public/protected view where enabled by company policy

## Required Permissions

Attendance self-service permissions approved by the company, such as Attendance.Attendance.RequestMidDayPermission.

Leave request permissions such as Leave.Leave.RequestEmergencyLeave and Leave.Application.Request.

View permissions for self-service pages as configured.

## Attendance Workflow

Open /Attendance/MyAttendance.

Review today status.

Start attendance session at the beginning of work.

Start and end break if break tracking applies.

End attendance session at the end of work.

If you forgot or were late, submit the approved request type if available.

## Mid-Day Permission Workflow

Open the attendance permission request page if available to your role.

Create request with date, time, and reason.

Submit request.

Monitor status until approved or rejected.

## Leave Application Workflow

Open /LeavesManagement/MyLeaveApplications.

Create a new leave application.

Select leave type and dates.

Add reason and attachment if required.

Save and submit.

Monitor status.

Cancel only when policy allows cancellation.

## Emergency Leave Workflow

Open /LeavesManagement/EmergencyLeaves.

Create emergency leave request.

Add attachment if required.

Submit request.

Follow up with manager/HR if urgent.

## Common Mistakes

| Mistake | Avoidance |
| --- | --- |
| Forgetting to end attendance session. | Check My Attendance before leaving work. |
| Submitting leave without attachment when required. | Prepare attachment before submission. |
| Selecting wrong dates. | Review start/end dates before submit. |
| Re-submitting duplicate requests. | Check existing request status first. |

## Troubleshooting

| Symptom | What to do |
| --- | --- |
| Cannot log in. | Contact IT support. |
| Cannot see attendance or leave page. | Contact HR/IT to verify role. |
| Attendance location is rejected. | Confirm location permission/device rules and contact Attendance Officer. |
| Leave balance looks wrong. | Contact HR Administrator. |

## Escalation

Attendance issues go to Attendance Officer. Leave balance or leave status questions go to HR Administrator. Login and access issues go to IT support.

# Chapter 25: User Guide: Manager and Supervisor

## Role Purpose

Managers and supervisors review team-related HR, attendance, and leave activity, approve requests where authorized, and support accurate team data.

## Main Pages

Employee list/view if authorized: /Employee/Employee/List

Attendance approvals: /Attendance/ApprovePermissionRequests

Late requests: /Attendance/LateRequests

Attendance reports: /Attendance/Reports

Leave approvals: /HR/LeaveApplications, /LeavesManagement/ApproveEmergencyLeaves

Leave reports: /LeavesManagement/Reports

Performance review pages where enabled: /HR/Performance

## Required Permissions

Employees.Employee.View

Attendance.Attendance.ReviewRequests

Attendance.Attendance.ApproveMidDayPermission

Attendance.Roster.ApproveSwap if roster swaps are in scope

Leave.Leave.ApproveEmergencyLeave

Leave.Application.Approve

HR.Performance.Review where performance reviews are in scope

## Attendance Approval Workflow

Open approval page.

Filter pending requests by date, employee, or status.

Review request reason and attendance context.

Approve or reject with clear comment.

Confirm status changes.

## Leave Approval Workflow

Open leave application or emergency leave approval page.

Review employee, dates, leave type, balance, attachment, and overlap risk.

Approve or reject according to company policy.

Add comment.

Confirm employee receives updated status.

## Team Review Workflow

Open employee or report page available to your role.

Filter by branch, department, or team where available.

Review missing data, attendance exceptions, or upcoming leave.

Escalate corrections to HR or attendance owner.

## Performance Workflow

Open /HR/Performance if activated.

Select appraisal cycle and employee.

Review goals and competency scores.

Add manager feedback.

Submit review or approve based on assigned authority.

Requires validation: exact manager authority and rating policy.

## Common Mistakes

| Mistake | Avoidance |
| --- | --- |
| Approving requests without checking dates or balance. | Review details before approval. |
| Leaving approvals pending. | Check approval pages daily during business days. |
| Trying to edit employee master data. | Send data corrections to HR unless your role permits edits. |
| Sharing payroll or employee data outside policy. | Follow confidentiality rules. |

## Troubleshooting

| Symptom | Check |
| --- | --- |
| Team member missing from report. | Branch/department/team assignment or manager scope. |
| Approval button missing. | Approval permission not assigned. |
| Cannot open performance page. | Performance module/role may not be enabled. |

## Escalation

Escalate employee data issues to HR Administrator, attendance issues to Attendance Officer, and access issues to IT.

# Chapter 26: User Guide: Payroll Officer

## Role Purpose

The Payroll Officer configures payroll masters, assigns payroll data to employees, runs payroll, reviews payslips, manages loans, handles WPS/Saudi payroll information, and coordinates payroll accounting posting where in scope.

## Main Pages

Payroll components: /Payroll/Components

Contracts: /Payroll/Contracts

Assign contracts: /Payroll/AssignContract

Salary runs: /Payroll/SalaryRuns

Employee loans: /Payroll/Loans

Salary structures: /HR/PayrollStructures

Work entries: /HR/WorkEntries

Payslips: /HR/Payslips

Saudi payroll: /HR/SaudiPayroll

## Required Permissions

Payroll.Contract.*

Payroll.Loan.*

Payroll.SalaryRun.*

Payroll.Structure.*

Payroll.Payslip.*

Payroll.WorkEntry.*

View access to employee and attendance data as approved.

Finance/accounting permissions if payroll posting is part of the role.

## Payroll Setup Workflow

Confirm employee records and assignments are approved.

Create payroll components.

Create contracts.

Assign employee contracts.

Create salary structures and assignments if used.

Create payroll periods.

Enter Saudi payroll and WPS information where required.

Validate employee loans.

## Monthly Payroll Workflow

Confirm attendance work entries and leave impacts are ready.

Create payroll entry or salary runs for the period.

Generate or calculate payroll.

Review payroll inputs, loans, deductions, and allowances.

Review payslips.

Recalculate if corrections are required.

Approve payroll output.

Mark payslips paid where applicable.

Create/export WPS batch if in scope.

Post payroll accounting if finance integration is approved.

## Employee Loan Workflow

Open /Payroll/Loans.

Create loan for employee.

Enter loan type, amount, schedule, and notes.

Submit or save according to company process.

Approve loan if authorized.

Cancel only according to approved payroll policy.

## Salary Run Workflow

Open /Payroll/SalaryRuns.

Create salary run for employee/contract/month/year.

Calculate salary run.

Review result.

Approve when correct.

Commit period after all runs are approved.

Undo salary run or period only with documented approval.

## Common Mistakes

| Mistake | Avoidance |
| --- | --- |
| Running payroll before employee data is approved. | Confirm HR data sign-off first. |
| Missing contract assignment. | Review employee contract list before payroll. |
| Approving payroll before leave/attendance validation. | Require attendance and leave cut-off confirmation. |
| Undoing committed payroll without approval. | Use payroll change approval. |
| Incorrect WPS/bank data. | Validate IBAN and bank fields before payroll. |

## Troubleshooting

| Symptom | Check |
| --- | --- |
| Employee missing from payroll. | Employee status, contract assignment, salary structure, branch access. |
| Payslip amount is wrong. | Components, payroll inputs, loans, work entries, leave impact. |
| Cannot approve payroll. | Payroll.SalaryRun.Approve or Payroll.Payslip.Approve permission. |
| WPS data missing. | Saudi payroll info and bank details. |

## Escalation

Escalate employee master data issues to HR. Escalate attendance work-entry issues to Attendance Officer. Escalate accounting posting issues to Finance Reviewer. Escalate access issues to IT.

# Chapter 27: User Guide: Specialist Roles

## Attendance Officer

### Purpose

Manage shifts, attendance sessions, exceptions, holidays, roster controls, biometric imports, work entries, and attendance reports.

### Main Pages

/Attendance/Dashboard

/Attendance/Sessions

/Attendance/Shifts

/Attendance/ShiftAssignments

/Attendance/Holidays

/Attendance/PermissionRequests

/Attendance/ApprovePermissionRequests

/Attendance/LateRequests

/Attendance/Reports

/HR/AttendanceRoster

/HR/WorkEntries

### Required Permissions

Attendance.Attendance.*

Attendance.Roster.*

Attendance.WorkEntry.*

### Daily Tasks

Review attendance dashboard.

Check exceptions and pending requests.

Maintain shifts and shift assignments.

Review sessions and missing check-ins.

Generate or approve work entries for payroll.

Review attendance reports.

## Recruiter

### Purpose

Manage staffing plans, job requisitions, applicants, interviews, offers, and hire handoff.

### Main Page

/HR/Recruitment

### Required Permissions

HR.Recruitment.Select

HR.Recruitment.View

HR.Recruitment.Create

HR.Recruitment.Edit

HR.Recruitment.Approve

HR.Recruitment.Hire

### Workflow

Create staffing plan.

Create and open job requisition.

Add applicants.

Record interview feedback.

Create job offer.

Accept/reject offer.

Mark employee created after HR creates the employee record.

Requires validation: approval authority, offer templates, and employee creation handoff.

## Performance Reviewer

### Purpose

Manage appraisal cycles, goals, competencies, evaluations, reviews, and approvals.

### Main Page

/HR/Performance

### Required Permissions

HR.Performance.Select

HR.Performance.View

HR.Performance.Create

HR.Performance.Edit

HR.Performance.Review

HR.Performance.Approve

### Workflow

Create appraisal cycle.

Define goals and competencies.

Start cycle.

Create employee evaluation.

Capture employee and manager feedback where enabled.

Recalculate, review, approve, or cancel evaluation.

Close cycle.

Requires validation: scoring, rating scales, weighting, calibration, and approval hierarchy.

## Training Coordinator

### Purpose

Manage training programs, events, attendees, attendance, results, certificates, and completion.

### Main Page

/HR/Training

### Required Permissions

HR.Training.Select

HR.Training.View

HR.Training.Create

HR.Training.Edit

HR.Training.Complete

### Workflow

Create training program.

Create training event.

Open and start event.

Add attendees.

Mark attendance.

Record results.

Link certificates.

Complete or cancel event.

Requires validation: nomination rules, certificate policy, and training budget controls.

## Finance Reviewer

### Purpose

Review payroll outputs and accounting impact where payroll accounting posting is in scope.

### Main Pages

/HR/Payslips

Payroll pages available to finance by policy

Accounting pages if finance module access is granted

### Typical Permissions

Payroll view/report permissions as approved.

Accounting document or journal permissions only where finance review is part of the implementation.

### Workflow

Review payroll summary with Payroll Officer.

Check approved payslips and totals.

Review payroll accounting posting if enabled.

Approve finance sign-off or raise exception.

## Executive or Management Viewer

### Purpose

Use dashboards and reports for oversight without maintaining operational records.

### Main Pages

/Employee/Dashboard

/Attendance/Dashboard

/Attendance/Reports

/LeavesManagement/Reports

/HR/Reports

Payroll reports/pages as approved

### Guidelines

Use view/report access only.

Do not approve operational requests unless explicitly assigned.

Escalate data discrepancies to the business owner.

# Appendix: Documentation Index

This package prepares a company implementation of AlafkarHR based on the repository capabilities inspected on 2026-06-30.

Confirmed system areas include organization setup, security roles and users, employees, employee lifecycle, employee documents, employee skills and certifications, attendance, roster control, leave management, payroll, recruitment, performance, training, reports, and general settings. When a workflow is not fully confirmable from the inspected code, the documents mark it as requiring business validation.

## Document Index

| File | Purpose |
| --- | --- |
| 01-implementation-plan.md | End-to-end rollout approach, phases, timeline, risks, governance, and success criteria. |
| 02-project-charter.md | Project authority, scope, goals, stakeholders, assumptions, and approval model. |
| 03-scope-of-work.md | Confirmed functional scope, excluded items, dependencies, and validation notes. |
| 04-stakeholder-register.md | Stakeholder groups, responsibilities, and engagement needs. |
| 05-raci-matrix.md | RACI ownership across implementation activities. |
| 06-data-migration-plan.md | HR data cleansing, migration, validation, and cutover approach. |
| 07-master-data-collection-template.md | Templates for companies, branches, departments, positions, shifts, leave, payroll, and HR masters. |
| 08-employee-data-collection-template.md | Employee profile, employment, attendance, leave, payroll, and document data templates. |
| 09-configuration-workbook.md | Configuration checklist for organization, security, HR, attendance, leave, payroll, and settings. |
| 10-roles-permissions-matrix.md | Recommended role model mapped to confirmed permission groups. |
| 11-workflow-mapping.md | Business process maps for daily HR operations and approvals. |
| 12-test-plan.md | SIT, UAT, regression, data, security, and go-live test coverage. |
| 13-uat-test-scripts.md | Role-based UAT scenarios and acceptance criteria. |
| 14-training-plan.md | Training audiences, agenda, materials, and attendance tracking. |
| 15-communication-change-plan.md | Communication, change management, readiness, and adoption plan. |
| 16-go-live-checklist.md | Go-live readiness checklist. |
| 17-cutover-plan.md | Cutover sequence, freeze windows, validation, and rollback decision points. |
| 18-support-hypercare-plan.md | Hypercare support process, triage, SLA, and handover. |
| 19-risk-issue-register.md | Starting risk and issue register. |
| 20-sign-off-templates.md | Sign-off templates for phase, data, UAT, training, and go-live approvals. |
| 21-post-go-live-review.md | Post-go-live review template and improvement backlog. |
| 22-user-guide-system-administrator.md | User guide for platform, company, security, role, and settings administrators. |
| 23-user-guide-hr-administrator.md | User guide for HR administration, employee records, and HR master data. |
| 24-user-guide-employee.md | User guide for employees using attendance, leave, and self-service pages. |
| 25-user-guide-manager.md | User guide for managers and supervisors handling approvals and team oversight. |
| 26-user-guide-payroll-officer.md | User guide for payroll setup, runs, payslips, loans, WPS, and Saudi payroll data. |
| 27-user-guide-specialist-roles.md | User guide for attendance officers, recruiters, performance, training, finance reviewers, and executives. |

## Confirmed Application Entry Points

| Area | Confirmed pages/routes |
| --- | --- |
| Security | /Auth/Dashboard, /Auth/Role/List, /Auth/Role/Form, /Auth/User/List, /Auth/User/Form, /Auth/User/AssignRole |
| Organization | /Organization/Dashboard, /Organization/Company/List, /Organization/Branch/List, /Organization/Administration/List, /Organization/Department/List, /Organization/BusinessLines, /Organization/LicenseCategories |
| Employees | /Employee/Dashboard, /Employee/Employee/List, /Employee/Employee/Form/{Id?}, /Employee/Employee/view/{Id}, /Employee/Employee/360/{Id}, /Employee/Teams, /Employee/Position/List, /Employee/AcademicInistitution/List, /Employee/Specialization/List |
| HR workspaces | /HR/CommandCenter, /HR/EmployeeLifecycle, /HR/EmployeeDocuments, /HR/EmployeeSkills, /HR/EmployeeEmergencyContacts, /HR/Recruitment, /HR/Performance, /HR/Training, /HR/Reports |
| Attendance | /Attendance/Dashboard, /Attendance/MyAttendance, /Attendance/Sessions, /Attendance/Shifts, /Attendance/ShiftAssignments, /Attendance/Holidays, /Attendance/PermissionRequests, /Attendance/ApprovePermissionRequests, /Attendance/LateRequests, /Attendance/Reports |
| Leave | /LeavesManagement/MyLeaveApplications, /LeavesManagement/EmergencyLeaves, /LeavesManagement/ApproveEmergencyLeaves, /LeavesManagement/Balances, /LeavesManagement/Reports, /HR/LeavePolicies, /HR/LeaveApplications, /HR/LeaveLedger |
| Payroll | /Payroll/Components, /Payroll/Contracts, /Payroll/AssignContract, /Payroll/SalaryRuns, /Payroll/Loans, /HR/PayrollStructures, /HR/WorkEntries, /HR/Payslips, /HR/SaudiPayroll |
| General Settings | /GeneralSettings/SystemSettings, /GeneralSettings/HomePageTemplates, /GeneralSettings/Currencies |

## Validation Notes

This documentation does not modify application behavior.

Permission names come from PermissionList.cs.

Page routes come from Blazor @page directives and menu metadata.

Recruitment, performance, and training service contracts are present; detailed customer-specific process rules still require business validation before go-live.